## Pre 94
SMART INTEGRATED MASTER PLAN (SIMP) FOR TITLE DEEDS - EASTERN CAPE METROPOLITAN AREAS
[14 empty] | Township Establishment: Planning Approvals; Beneficiary Verification & Conveyancing | [8 empty] | Construction Phase: Bulk / Internal Reticulation / Housing Dev
Province | Local Municipality | Regional Area | Project Name / Scheme | Property Description of Parent Property | Departmental Stock (DS) / Municipal Stock (MS) | Is The Project Part of the MTSF i.e. 2024- 2029 (Yes or No) | Is The Project In The Current Business Plan i.e.2023/24 (Yes or No) | Annual Budget 2023/24 | Source of Funding | No. of Units Constructed | No. of Properties Transferred | Balance of Properties To Transfer | Project Generic Milestone | Service Provider Appointed (Yes/No) | Is The Project Spatial Referenced (GIS Polygon Created) (Yes/No) | Land Issues / Land Assembly Resolved (Yes/No) | Town Planning Approval - (Layout Approved) (Yes/No) | Condition of Establishment (COE's) Approved (Yes/No) | GP Approved (Yes/No) GP No. | Services / Compliance Certificate In Place (Yes/No) | Township Register Opened (Yes/No) | Beneficiary Verification | No. of Sales Agreement Signed | No. of EEDBS Forms Completed & Scheduling For Approval | Scheduling Income R0 - R1 500 | Scheduling Income R1501 - R3500 | Scheduling Income R3501 - R7000 | Scheduling Income R7000 - Above | Comments
Eastern Cape | Buffalo City | Coastal | Buffalo Flats |  | Municipal Stock |  |  |  |  | 195 | 191 | 4 | Beneficiary Management | [15 empty] | Beneficiary verification is required & this project may be affected by beneficiary issues.
Eastern Cape | Buffalo City | Coastal | Buffalo Flats Ext 1 |  | Municipal Stock |  |  |  |  | 492 | 482 | 10 | Beneficiary Management | [15 empty] | Beneficiary verification is required & this project may be affected by beneficiary issues.
Eastern Cape | Buffalo City | Coastal | Buffalo Flats Ext. 2 - 6 |  | Municipal Stock |  |  |  |  | 2873 | 2714 | 159 | Beneficiary Management | [15 empty] | Beneficiary verification is required & this project may be affected by beneficiary issues.
Eastern Cape | Buffalo City | Coastal | Charles Lloyd |  | Municipal Stock |  |  |  |  | 234 | 221 | 13 | Beneficiary Management | [15 empty] | Beneficiary verification is required & this project may be affected by beneficiary issues.
Eastern Cape | Buffalo City | Coastal | Parkridge 136, 69 ,47 |  | Municipal Stock |  |  |  |  | 252 | 180 | 72 | Beneficiary Management | [15 empty] | Houses Dilapited and needs Rectification, this is therefore likely to affect other milestones leading to the intended transfer i.e. property registrations.
Eastern Cape | Buffalo City | Coastal | Pefferville |  | Municipal Stock |  |  |  |  | 176 | 154 | 22 | Beneficiary Management | [15 empty] | Beneficiary verification is required & this project may be affected by beneficiary issues.
Eastern Cape | Buffalo City | Coastal | Parkside 456 |  | Municipal Stock |  |  |  |  | 456 | 433 | 23 | Beneficiary Management | [15 empty] | Beneficiary verification is required & this project may be affected by beneficiary issues.
Eastern Cape | Buffalo City | Coastal | Parkside Lavender Self Help |  | Municipal Stock |  |  |  |  | 25 | 25 | 0 | Completed | [15 empty] | Project completed; BCMM to provide update regarding the close out report.
Eastern Cape | Buffalo City | Coastal | Buffalo Flats Canterbury Self Help |  | Municipal Stock |  |  |  |  | 130 | 124 | 6 | Beneficiary Management | [15 empty] | SELF -HELP Project (similar to People housing. Beneficiary verification is required & this project may be affected by beneficiary issues.
Eastern Cape | Buffalo City | Coastal | Braelyn |  | Municipal Stock |  |  |  |  | 463 | 448 | 15 | Beneficiary Management | [15 empty] | Beneficiary verification is required & this project may be affected by beneficiary issues.
Eastern Cape | Buffalo City | Coastal | Cambridge location |  | Municipal Stock |  |  |  |  | 117 | 110 | 15 | Beneficiary Management | [15 empty] | Confirmation on the no. of transferred versus balance to transfers needs to be corrected. Beneficiary verification is required & this project may be affected by beneficiary issues.
Eastern Cape | Buffalo City | Coastal | Gompo,D/ Village Proper / Dunga |  | Municipal Stock |  |  |  |  | 1021 | 913 | 186 | Township Establishment | [15 empty] | State land, Subdivision,Recrification,Previous Subsidy
Eastern Cape | Buffalo City | Coastal | Milner Estate |  | Municipal Stock |  |  |  |  | 171 | 155 | 16 | Beneficiary Management | [15 empty] | Beneficiary verification is required & this project may be affected by beneficiary issues.
Eastern Cape | Buffalo City | Coastal | Stoneydrift |  | Municipal Stock |  |  |  |  | 141 | 138 | 3 | Beneficiary Management | [15 empty] | Beneficiary verification is required & this project may be affected by beneficiary issues.
Eastern Cape | Buffalo City | Coastal | CPA Camp (Summerpride) |  | Municipal Stock |  |  |  |  | 44 | 42 | 2 | Beneficiary Management | [15 empty] | Houses sold to beneficiaries occupying. Beneficiary verification is required & this project may be affected by beneficiary issues.
|  | Coastal | Panmure |  | Municipal Stock |  |  |  |  | 104 | 104 | 0 | Completed | [15 empty] | Project completed; BCMM to provide update regarding the close out report.
|  | Coastal | Brookville |  | Municipal Stock |  |  |  |  | 80 | 80 | 0 | Completed | [15 empty] | Project completed; BCMM to provide update regarding the close out report.
|  | Coastal | Morningside |  | Municipal Stock |  |  |  |  | 324 | 324 | 0 | Completed | [15 empty] | Project completed; BCMM to provide update regarding the close out report.
Eastern Cape | Buffalo City | Inland | Illitha South |  | Municipal Stock |  |  |  |  | 820 | 689 | 131 | Township Establishment | [15 empty] | Wooden Houses, Rectification, Subdivision and sharing units
Eastern Cape | Buffalo City | Inland | Zwelitsha |  | Municipal Stock |  |  |  |  | 3452 | 3442 | 10 | Township Establishment | [15 empty] | State Land, Sub-division
Eastern Cape | Buffalo City | Inland | Pakamisa |  | Municipal Stock |  |  |  |  | 986 | 969 | 17 | Township Establishment | [15 empty] | Rectification, Sub-division
Eastern Cape | Buffalo City | Inland | Dimbaza |  | Municipal Stock |  |  |  |  | 1985 | 1954 | 16 | Township Establishment | [15 empty] | State Land, Rectification, subdivision
Eastern Cape | Buffalo City | Inland | Ginsberg |  | Municipal Stock |  |  |  |  | 393 | 350 | 93 | Township Establishment | [15 empty] | Stateland, Rectification
Eastern Cape | Buffalo City | Inland | Breidbach |  | Municipal Stock |  |  |  |  | 310 | 289 | 21 | Beneficiary Management | [15 empty] | Beneficiary verification is required & this project may be affected by beneficiary issues.
Eastern Cape | Buffalo City | Inland | Schonville |  | Municipal Stock |  |  |  |  | 143 | 140 | 9 | Beneficiary Management | [15 empty] | Confirmation on the no. of transferred versus balance to transfers needs to be corrected. Beneficiary verification is required & this project may be affected by beneficiary issues.

## Post 94
SMART INTEGRATED MASTER PLAN (SIMP) FOR TITLE DEEDS - EASTERN CAPE METROPOLITAN AREAS
PROJECT LOCATION INFORMATION | [5 empty] | PROJECT BASIC INFORMATION |  |  |  |  | PROJECT CONTRACTUAL OBLIGATIONS | [8 empty] | PROJECT PROGRESS SECTION | [6 empty] | TOWNSHIP ESTABLISHMENT ACTIVITIES | [11 empty] | BV & TRANSFERS |  | PROJECT IMPLEMENTATION UPDATES
Province | Regional / District Municipality | Local Municipality | Regional Area | Lat Deg (X Coordinate) | Long Deg (Y Coordinate) | Project Name | HSS Project No. | Parent Property Description & Registered Owner | Subsidy Instrument (To be Obtained From HSS) /Historical Project (Yes/No) | Project Type | Project Start Date | Project End Date | Total Project Value Approved | Total Accumulative Expenditure To Date | Is The Project Part of the MTDP i.e. 2024- 2029 (Yes or No) | Is The Project In The Current Business Plan i.e.2024/25 (Yes or No) | Annual Budget 2024/25 | Source of Funding | Project Implemented By ECDHS / BCMM | Yield | No of Beneficiaries Approved | No. of Serviced Stands | No. of Units Constructed | No. of Properties Transferred | Balance of Properties To Transfer | Project Generic Milestone | Service Provider Appointed (Yes/No) or N/A | Is The Project Spatial Referenced (GIS Polygon Created) (Yes/No) | Land Issues / Land Assembly Resolved (Yes/No) | Enviromental Impact Assessment Approved (Yes/No) | Water Use License Obtained (Yes/No) | SPLUMA (Layout / Settlement Plan) Approved (Yes/No) Layout No. | Condition of Establishment Approved (Yes/No) | GP Approved (Yes/No) GP No. | Bulk Infrastructure In Place (Yes/No or N/A) | Internal Reticulation In Place i.e. Water & Sanitation (Yes/No) | Services / Compliance Certificate In Place (Yes/No) | Township Register Opened (Yes/No) Proclaim No. / Gazette No. | Beneficiary Verification | Transfers | NHBRC Assessment Report (Yes/No) or N/A | Current Project Status (Active/Blocked or N/A) | Comments / Updates | Recommended Action To Take The Project Forward | Planning Unit | Land Survey | ECDHS Report Findings | Housing Delivery & Implementantion Department Report
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Inland |  |  | KWT - Breidbach 531 subs (Phase) | C17090001/1 - 2 |  | Post 2014 (2015 - 2018) | Progress Payment Housing Project | 2018-05-30 | 2024-06-30 | 133553369.52 | 30517731.41 |  | No | 0 |  | ECDHS | 531 | 250 | 0 | 0 |  |  | Township Establishment | [16 empty] | It is not clear out of the 2 HSS project (Breidbach) which one should be the correct project name to use going forward. | ECDoHS to confirm the correct HSS project name & also should provide the status quo report for further scrutiny. | In one of the Breidbach project the ECDHS they intended to densify the existing GP, ECDHS to provide updates. | In one of the Breidbach project the ECDHS they intended to densify the existing GP, ECDHS to provide updates. | New project & planning activities to be reported by BCMM Planning.
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Midlands | -32.5439 | 27.864217 | East London - St Lukes 203 subs ( - Utshani 143 subs) | C13110002/1 -2 | Erf 4651 Newlands registered under BCMM | Post 94 (1994 - 2014) | Peoples Housing Process (IRDP) | 2019-10-18 | 2022-12-08 | 32562970.6 | 29464777.72 | Yes | Yes | 2562933 |  | ECDHS | 203 | 203 | 155 | 147 | 0 | 203 | Township Establishment | [7 empty] | GP518/2010 | [7 empty] | Active |  |  | The land was donated by the church (Dioysis) to the community. Planning applications to be confirmed by the ECDHS. GP SG no. 518 / 2010. | GP SG no. 518 / 2010 is confirmed & has about 210 erven located on parent property Erf 4651 Newlands registered under BCMM , therefore BCMM infrastructure to confirm the availability of services. | ECDHS report suggest that the project is rural;however BCMM indicate that it is an IRDP hence contradictions observed regrding GP & BCMM.
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Coastal |  |  | East London - Scenery Park Ph 1 - 1160 subs (Phase 1) | C95010001/1 - 2 |  | Post 94 (1994 - 2014) | Progress Payment Housing Project | 2014-03-31 | 2022-09-30 | 132366123.9 | 113708295.5 |  | No | 0 |  | ECDHS | 1160 | 1163 | 9 | 507 |  |  | Township Establishment | [18 empty] | There is a GP approval & Geometics to assist with GP information. TR hasn’t been approved yet & exemption granted by BCMM Planning to allow for the opening of township register. Next move is to plan a meeting with Land Use Planning team for confirmation of compliance certificate prior to engagging BCMM Property Mng (Lizeka) or ECDHS to confirm the status of the project & TR. | There is a GP approval & Geometics to assist with GP information. TR hasn’t been approved yet & exemption granted by BCMM Planning to allow for the opening of township register. Next move is to plan a meeting with Land Use Planning team for confirmation of compliance certificate prior to engagging BCMM Property Mng (Lizeka) or ECDHS to confirm the status of the project & TR. | Updates on bulk & internal services corfimed
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Coastal |  |  | East London - Airport Phase 2a - 614 subs (Phase 1) | C03030002/1 |  | Post 94 (1994 - 2014) | Peoples Housing Process (IRDP) | 2003-05-21 | 2023-06-30 | 38832754.63 | 32877544.6 |  | No | 0 |  | ECDHS | 614 | 613 | 229 | 283 | 0 | 614 | Beneficiary Management | [7 empty] | GP 645/2003 | [8 empty] | Land is not yet subdivided hence no transfers achieved to date. | Confirmation regarding the appointment of the service provider to deal with outstanding township establishment (TE) is required urgently from both the EC DoHS & BCMM, this includes confirmation of availability of funds to complete the TE milestones. | ECDHS to confirm whether the project is the same as Siyakha project, if yes than it be noted that there is a GP 645/2003 in place & due to required amendment LM town planning granted 5 year extension to accommodate amendments. (SP Thoba Mkhangisi & Associates). The mentioned extension is still valid. | ECDHS to confirm whether the project is the same as Siyakha project, if yes than it be noted that there is a GP 645/2003 in place & due to required amendment LM town planning granted 5 year extension to accommodate amendments. (SP Thoba Mkhangisi & Associates). The mentioned extension is still valid. | The PRM mentions Airport Phase 2 consisting of 195 subs (C9804000) & yet the NDHS HSS project list mentions Airport phase 2 with 614 subs (C03030002/1).
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Coastal |  |  | East London - Duncan Village - 352 subs (Phase 1) | C00110001/1; C09090002/1 |  | Post 94 (1994 - 2014) | Peoples Housing Process (IRDP) | 1998-01-15 | 2023-03-13 | 10474380.66 | 10163673.78 |  | No | 0 |  | ECDHS | 352 | 353 | 352 | 7 |  |  | Township Establishment | [18 empty] | ECDHS to confirm project location & property description, because without those co ordinate it is impossible to determine the status of township establishment process. | ECDHS to confirm project location & property description, because without those co ordinate it is impossible to determine the status of township establishment process. | Updates on bulk & internal services corfimed. Rectification
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Coastal |  |  | East London - Kaysers Beach Lily Vale - 88 subs (Phase 1) | C01030019/1 | Erf 1 Lillyvale registered under BCMM | Post 2014 (2015 - 2018) | Progress Payment Housing Project | 2015-05-01 | 2019-12-31 | 15095787.1 | 14549685.8 |  | No | 0 |  | ECDHS | 88 | 88 | 88 | 88 |  |  | Township Establishment | [18 empty] | Town planning approval obtained with ref 2810/TP (LM ref) dated 12-08-2009. BCMM Property Mng to confirm the status of the TR. | The project is located on Erf 1 Lillyvale registered under BCMM & there is a GP 3958/2009 in place. BCMM Infrastructure & Property Mng to confirm the status of the TR. | According to ECDHS Kaysers Beach (Urban) & Lily Vale (Rural) are two different projects, therefore contradictions between National & Provincial Department regarding project name. Kaysers is one of rectification projects & has both bulk and internal srvices available. | Township register not opened. Property Management await receipt of approved General plan and subdivisional approval under a cover of a memorandum from Develolpment Planning requesting registration of the township register. Paragaph taken from muicipal responses.
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Inland |  |  | East London - Berlin - 411 subs (Phase 1) | C01050004/1 |  | Post 94 (1994 - 2014) | Progress Payment Housing Project | 2001-05-22 | 2022-06-30 | 7655580 | 7655280 |  | No | 0 |  | ECDHS | 411 | 411 | 411 | 411 |  |  | Township Establishment | [19 empty] | ECHDS to provide property description for the project & status quo thereof | The project is not known by ECDHS team
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Midlands | -32.5842 | 27.3616 | East London - Chris Hani - 304 subs (Phase 1) | C01080001/1; C10010001/1 |  | Post 94 (1994 - 2014) | Peoples Housing Process (IRDP) | 2001-11-08 | 2022-06-30 | 9970893.15 | 9970893.15 | Yes | Yes | 6190400 |  | ECDHS | 304 | 304 | 302 | 141 |  |  | Township Establishment | [15 empty] | Blocked |  | ECDHS to confirm the correct HSS project urgently to enable world bank team to scrutinize futher. | ECDHS report suggest that there is a TR opened for this project. | According to LS, the GP cannot be confirmed yet, therefore ECDHS is required to confirm the detailed project status quo on TE processes. | Updates on bulk & internal services corfimed (Rectification). According to the BP R630 400 budgeted for transfers of 20 properties, the target is unrealistic.
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Midlands | -32.5842 | 27.3616 | East London - Mdantsane Zone CC - 427 sites (Phase 1) | C97120014/1 | Erf 2106 Mdantsane CC registered under XXXXX | Post 94 (1994 - 2014) | Peoples Housing Process (IRDP) | 1997-09-01 | 2023-02-22 | 10672115.31 | 10512173.31 | Yes | Yes | 1245920 |  | ECDHS | 427 | 426 | 427 | 183 |  |  | Township Establishment | [7 empty] | GP: C8/1996 | [7 empty] | Active |  |  | Mdantsane Zone CC 427 & Mdantsane Zone 18 cc 1 500 is one project area that has Town Planning approval & GP in place. To date installation of services is being undertaken, however BCMM report suggest that there is a TR in place somehow confirmation is required urgently from ECDHS. | GP no. C8/1996 is in place & consist of a total of 986 erven located on parent property Erf 2106 Mdantsane CC. According to the evidence for the project area there are some parts where transfers have been undertaken and with construction activities being undertaken. Project Managers to provide project progress report. | According to the 2024/25 BP R145 920 is bidgeted for tranfers of 96 properties, the target is unrealistic.
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Inland |  |  | KWT - Dimbaza 27 subs (Phase 1) | C13020022/1 |  | Post 94 (1994 - 2014) | Progress Payment Housing Project | 2015-08-17 | 2023-02-28 | 5421859.2 | 4080855.7 |  | No | 0 |  | BCMM | 27 | 27 | 27 | 27 | 27 | 27 | Township Establishment | [16 empty] | The received municipal report has contradicting information on this project i.e. the municipal report indicate that all transfers have been achieved, while at the same time indicate that no transfers undertaken. Confirmation is required. | BCMM: Is required to provide clarity on conveyancing activities since contradictions have been observed i.e. no. of transferred properties versus properties to be transferred. | Township has been upgraded in terms of the land tenure (SPLUMA) for the whole Dimbaza township including pre 94 housing. | GP is confirmed & in place for Dimbaza area | GP is confirmed & in place for Dimbaza area
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Inland |  |  | Berlin - Dongwe - 300 subs (Phase 1) | C01030017/1 - 2 |  | Post 94 (1994 - 2014) | Peoples Housing Process (IRDP) | 2003-11-10 | 2022-12-08 | 6774709.42 | 6774709.42 |  | No | 0 |  | ECDHS | 300 | 299 | 0 | 179 | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | ECHDS to provide property description for the project & status quo thereof | Rural project therefore certain milestones are not applicsable.
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Inland |  |  | KWT - R/land Ph 1 (Tyutyu) - 300 subs (Phase 1) | C00010001/1 |  | Post 94 (1994 - 2014) | Peoples Housing Process (IRDP) | 2000-11-20 | 2001-03-20 | 10764290 | 10764290 |  | No | 0 |  | BCMM | 300 | 300 | 300 | 300 |  |  | Transfer Stage | [16 empty] | The municipal report has combined two different HSS projects. BCMM to separate the two projects as per their HSS numbers to enable for efficiency and proper reporting and accountability i.e.It looks like both project are at transfer stage, yet SIMP reflect that, confirmation is required. | For future reporting it is recommeded that projects be separated in to two in line with the HSS records by both BCMM & ECDOHS to enable for proper accountability. | ECDHS to provide property description, however according to planning the GP are in place for the whole project area. Planning approval obtained around 2005/6 fy. | ECDHS to provide property description, however according to planning the GP are in place for the whole project area. Planning approval obtained around 2005/6 fy. | Both ECDHS & BCMM to update progress relating to transfers in column W & X
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Coastal | -32.9987 | 27.6464 | East London - Gonubie Mzamomhle - 548 subs (Phase 1) | C00030003/1 & C08100006/1 - 3 | Erf 69188 East London registered under BCMM | Post 94 (1994 - 2014) | Progress Payment Housing Project | 2000-04-01 | 31/03/2023 | 111050247.4 | 109379532.37 | Yes | Yes | 1503233 |  | ECDHS | 548 | 540 | 548 | 540 |  |  | Township Establishment | [7 empty] | GP 827/2009 | [7 empty] | Active |  |  | Houses have been built and the project implemented by ECDHS. The project is a duplication because it should be recorded as Gornubie Mzamomhle - 548 subs (Phase 1) C00030003/1. This project has an approved layout (18/01/2010) which has a total number of 548 sites of which 540 is for residential purposes. There is also disrepencies between the land owner that sold the land to ECDHS regarding none residential properties which he says he only sold residential sites. | Houses have been built and the project implemented by ECDHS. The project is a duplication because it should be recorded as Gornubie Mzamomhle - 548 subs (Phase 1) C00030003/1. The project is located on Erf 69188 East London registered under BCMM & has GP 827/2009 in place consisting of a total number of 548 sites of which 540 is for residential purposes. | Updates on bulk & internal services corfimed. According to the 2024/25 BP R9 966 is budgeted for 6 transfers.
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Coastal | -32.5499 | 27.6743 | East London - Alphendale - 339 subs (Phase 1) | C00060004/1; C09090001/1 | Erf 73682 East London & land ownership status is required. | Post 94 (1994 - 2014) | Peoples Housing Process (IRDP) | 1996-02-01 | 1999-09-30 | 13265939.08 | 13265939.08 | Yes | Yes | 2860000 |  | ECDHS | 339 | 339 | 322 | 329 |  |  | Beneficiary Management | [15 empty] | Active |  | BCMM to provide confirmations and ECDoHS to provide status quo report. | This project has a township register & needs certain confirmations from ECDHS regarding progress to date on construction of houses & transfers. | The project is located on Erf 73682 East London & land ownership status is required. There is a GP 827/2009 in place. This project has a township register & needs certain confirmations from ECDHS regarding progress to date on construction of houses & transfers. | The PRM is silent on the status of internal services & township register, hence ECDHS needs to confirm & update on progress. This project is a duplication with the one on column no. 113 rectification. Rectification is for 49 units & reporting on transfers will be obtained from Mr Fihla.
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Coastal |  |  | East London - Haven Hills v/d Leij p/linked - 132 subs (Phase 1) | C00070005/1 |  | Post 94 (1994 - 2014) | Progress Payment Housing Project | 2002-03-26 | 2002-12-31 | 2345636 | 2345636 |  | No | 0 |  | ECDHS | 132 | 132 | 132 | 132 |  |  | Township Establishment | [18 empty] | All Haven Hills are to be reported by the ECDHS regarding status quo | All Haven Hills are to be reported by the ECDHS regarding status quo | Urban project should be reffered back to BCMM
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Coastal |  |  | East London - Haven Hills v/d Leij Creditlinked - 70 subs (Phase 1) | C00070007/1 |  | Post 94 (1994 - 2014) | Progress Payment Housing Project | 2002-03-26 | 2002-12-31 | 0 | 0 |  | No | 0 |  | ECDHS | 70 | 0 | 0 | 0 |  |  | Township Establishment | [16 empty] | KWT - R/land Ph 2 (Tyutyu) - 373 subs (Phase 1) C01100018/1 |  | All Haven Hills are to be reported by the ECDHS regarding status quo | All Haven Hills are to be reported by the ECDHS regarding status quo | Urban project should be reffered back to BCMM. This project is location is the same as Haven Hills (C00070005/1) above therefore possibly may share one TR.
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Coastal | -33.0318 | 27.8405 | East London - Kaysers Beach - 61 subs (Phase 1) | C01010005/1 - 2 |  | Post 94 (1994 - 2014) | Progress Payment Housing Project | 2001-01-23 | 28/02/2023 | 9237477 | 8888859.49 | Yes | Yes | 346800 |  | ECDHS | 61 | 61 | 61 | 61 |  |  | Township Establishment | [7 empty] | SG 7492/1996 | [7 empty] | Active | It looks like both project are at transfer stage, yet SIMP reflect that, confirmation is required |  | GP is in place SG No.7492 of 1996. BCMM Property Management (Lizeka) to confirm the status of the TR. | GP is in place SG No.7492 of 1996. BCMM Property Management (Lizeka) to confirm the status of the TR. | Updates on bulk & internal services corfimed. Rectification 50.
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Inland |  |  | KWT - R/land Ph 1 (Ilitha) - 439 subs (Phase 1) | C01010006/1 |  | Post 94 (1994 - 2014) | Peoples Housing Process (IRDP) | 2001-01-30 | 2001-03-30 | 33948280.43 | 33948280.43 |  | No | 0 |  | ECDHS | 439 | 434 | 409 | 439 |  |  | Township Establishment | [18 empty] | ECDHS to provide property description, however according to planning the GP are in place for the whole project area. Planning approval obtained around 2005/6 fy. | ECDHS to provide property description for confirmation of TE milestones. | Updates on bulk & internal services corfimed
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Midlands |  |  | East London - R/land Ph 1 (Reeston) 4264 - Services only (Phase 1) | C01020004/1; C01020004/1; C07020001/1; C01020013/1 C01020014/1; C04080002/1; C04080003/1; C09020004/1 |  | Post 94 (1994 - 2014) | Peoples Housing Process (IRDP) | 2002-02-08 | 13/03/2023 | 253104647.36 | 252078859.39 |  | No | 0 |  | ECDHS | 4264 | 3888 | 1000 | 3532 |  |  | Township Establishment | [18 empty] | ECDHS to provide property description and project status quo report. | ECDHS to provide property description and project status quo report. | Project refer it back to BCMM for Township establishment milestones.
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Coastal |  |  | East London - Needscamp - 300 subs (Phase 1) | C01030020/1 | Erf 1444 Needscamp registered under BCMM | Post 94 (1994 - 2014) | Peoples Housing Process (Rural) | 2002-08-01 | 2003-03-01 | 6311679.82 | 6311679.82 |  | No | 0 |  | ECDHS | 300 | 300 | 0 | 292 |  |  | Township Establishment | [7 empty] | GP 7307/1992 | [10 empty] | There is a GP approval for Needscamp GP No.7307/1992, so land use Mng to confirm the status of compliance certificate issuing. ECHDS to give more info on status quo | The project is located on Erf 1444 Needscamp registered under BCMM & GP GP No.7307/1992 is in place. Engineering & Land use Mng to confirm the status of the project. ECHDS to give more info on status quo | ECDHS report suggest that the project is rural;however BCMM indicate that it is an IRDP hence contradictions observed regrding GP & BCMM. Rural usually have no bulk services & GP is not applicable. Confirmation to be obtained from Mjo.
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Inland |  |  | KWT - R/land Ph 2 (Tyutyu) - 373 subs (Phase 1) | C01100018/1 |  | Post 94 (1994 - 2014) | Peoples Housing Process (IRDP) | 2002-01-11 | 2002-12-31 | 33660061.62 | 33660061.62 |  | No | 0 |  | ECDHS | 373 | 368 | 373 | 49 |  |  | Transfer Stage | [16 empty] | The municipal report has combined two different HSS projects. BCMM to separate the two projects as per their HSS numbers to enable for efficiency and proper reporting and accountability i.e.It looks like both project are at transfer stage, yet SIMP reflect that, confirmation is required. | For future reporting it is recommeded that projects be separated in to two in line with the HSS records by both BCMM & ECDOHS to enable for proper accountability. | ECDHS to provide property description, however according to planning the GP are in place for the whole project area. Planning approval obtained around 2005/6 fy. | ECDHS to provide property description, however according to planning the GP are in place for the whole project area. Planning approval obtained around 2005/6 fy. | The identified Tyutyu 200 subs in the PRM has no HSS number & this makes it difficult to confirm the project on NDHS HSS project list.
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Coastal |  |  | East London - R/land Ph 2 (Nompumelelo) - 1199 subs (Phase 1) | C01100054/1 |  | Post 94 (1994 - 2014) | Peoples Housing Process (IRDP) | 2002-01-11 | 2022-03-31 | 38685014.89 | 38546079.89 |  | No | 0 |  | BCMM | 1199 | 1199 | 1199 | 1199 | 1181 | 18 | Transfer Stage | [16 empty] | There are about only 18 outstanding transfers & BCMM has about 12 un issued title deeds that needs to be handed over to the correct beneficiaries. | EC DoHS: To provide progress report on the balance of 18 outstanding transfers. BCMM: To provide update on the remaining 12 un issued title deeds to be handed to the rightful beneficiaries. | EC DoHS: To provide progress report on the balance of 18 outstanding transfers. BCMM: To provide update on the remaining 12 un issued title deeds to be handed to the rightful beneficiaries. | EC DoHS: To provide progress report on the balance of 18 outstanding transfers. BCMM: To provide update on the remaining 12 un issued title deeds to be handed to the rightful beneficiaries. | Both ECDHS & BCMM to update progress relating to transfers in column W & X
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Inland |  |  | KWT - Sweetwaters R/Land Ph3 : 620 subs (Phase 1) | C01120004/1 - 2 |  | Post 94 (1994 - 2014) | Peoples Housing Process (IRDP) | 2002-01-11 | 2015-08-22 | 58960584.96 | 58960584.96 |  | No | 0 |  | ECDHS | 620 | 602 | 587 | 572 | 527 | 527 | Township Establishment | [16 empty] | ??? According to this report 527 properties have been transferred & yet 527 is the outstanding not yet transferred properties & 166 is with BCMM. Confirmation required from BCMM, which is which? | BCMM to confirm conveyancing activities for this project i.e. Number of total transfers achieved to date and existing backlog to transfer as well as the number of unissued title deeds that are with the municipality. | GP is in place & land use management to confirm the status of compliance certificate. | GP is in place & land use management to confirm the status of compliance certificate. | Updates on bulk & internal services corfimed
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Coastal | -32.935 | 27.4615 | East London - Cambridge Ext 3 - 198 Php subs (Phase 1) | C02070002/1 - 2 |  | Post 94 (1994 - 2014) | Peoples Housing Process (IRDP) | 2002-07-01 | 2002-08-31 | 15438106.56 | 15438106.56 | Yes | Yes | 3774790 |  | ECDHS | 198 | 193 | 198 | 194 |  |  | Township Establishment | [15 empty] | Blocked | It is not clear out of the 4 HSS project (Cambridge) which one should be the correct project name to use going forward | ECDoHS to confirm the correct HSS project name & also should provide the status quo report for further scrutiny. | ECDHS to give status / progress report on this project in relation to milestones. | ECDHS to give status / progress report on this project in relation to milestones. | Updates on bulk & internal services corfimed (Rectification). According to the BP R106 400 budgeted for transfers of 70 properties, the target is unrealistic.
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Coastal | -32.9378 | 27.2919 | East London - Ducats - 625 subs (Phase 1) | C03030003/1 - 2 |  | Post 94 (1994 - 2014) | Peoples Housing Process (Rural) | 2015-01-01 | 2019-01-01 | 13183163.95 | 13167283.95 | Yes | Yes | 732000 |  | ECDHS | 625 | 624 | 625 | 528 |  |  | Township Establishment | [7 empty] | GP 3086/2002 | [7 empty] | Blocked |  |  | GP is in place no. 3086/2002 however there are pocket of properties that are registered under Amathole District Municipality. | GP is in place no. 3086/2002 however there are pocket of properties that are registered under Amathole District Municipality. | The PRM indicates that this project has no bulk services & is blocked (it was under Amathole District). Contradicting information btw ECDHS & BCMM report i.e. according to this report the project has no GP, yet BCMM survey say there is a GP in place. Confirmation is required whether the project is rural or not. Rectification.
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Midlands | -32.9423 | 28.0098 | Macleantown 77 subs (Phase 1) | C03030004/1 | Erven 564 & 565 registered under Amathole District and Erven 502;46;75;83;113;123 & 131 | Post 94 (1994 - 2014) | Peoples Housing Process (IRDP) | 2002-09-19 | 2015-12-31 | 7340516.06 | 7340516.06 | Yes | Yes | 1117722.5 |  | ECDHS | 77 | 77 | 0 | 49 |  |  | Township Establishment | [7 empty] | GP 1342/2003 | [7 empty] | Active |  |  |  | There are two GP's observed under Macleatown i.e. GP 1343/2003 located on parent Erven 564 & 565 registered under Amathole District & consists of 23 Erven. The second GP no. 1342/2003 located on numerous parent properties Erf502;46;75;83;113;123 & 131 and consists of 89 ervens and together once GP's are combined equates to 112 Erven. There seems to be no transfers to date. | According to this report this project is a rural project & hence no GP, but BCMM is reflecting that the project has GP. Contradiction identified between NDHS (HSS); BCMM & ECDHS reports.
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Coastal |  |  | East London - Scenery Park Secondary Owners 59 subs (Phase 1) | C03090001/1 |  | Post 94 (1994 - 2014) | Progress Payment Housing Project |  |  | 1622913 | 1622913 |  | No | 0 |  | ECDHS | 59 | 59 | 0 | 59 |  |  | Township Establishment | [18 empty] | ECDHS provincial to confirm the status of this project & location thereof. | ECDHS provincial to confirm the status of this project & location thereof. | The project is part of the mother project known as Scenery Park 160, this was an insitu project.
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Inland |  |  | KWT - Bulembu :508 subs (Phase 1) | C03110007/1; C09120006/1 |  | Post 94 (1994 - 2014) | Peoples Housing Process (Rural) |  |  | 10031954.92 | 10031954.92 |  | No | 0 |  | ECDHS | 508 | 504 | 0 | 244 |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | ECDHS provincial to confirm the status of this project & location thereof. | ECDHS provincial to confirm the status of this project & location thereof. | Rural project therefore certain milestones are not applicable. Rectification 424.
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Midlands |  |  | East London - Potsdam Unit P - 500 subs (Phase 1) | C04040021/1 | Erf 5295 Potsdam registered under BCMM | Post 94 (1994 - 2014) | Peoples Housing Process (IRDP) | 2011-11-14 | 2012-11-14 | 21139167.42 | 21139167.42 |  | No | 0 |  | ECDHS | 500 | 500 | 138 | 331 |  |  | Transfer Stage | [7 empty] | GP 343/2004 | [8 empty] | It is not clear out of the 2 HSS project (Potsdam Unit P) which one should be the correct project name to use going forward | ECDoHS to confirm the correct HSS project name & also should provide the status quo report for further scrutiny. | Planning approval obtained in terms of LEFTEA between 2004 & 2006 on Erf 5295 Potsdam covering all Potsdam Unit P projects | There is a GP no. 343/2004 in place situated on Erf 5295 Potsdam registered under BCMM & consists of 2 528 erven covering all Potsdam Unit P projects. There are transfers that have taken place. | Both ECDHS & BCMM to update progress relating to transfers in column W & X
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Midlands |  |  | East London - Z Soga 171 subs (Phase 1) | C04040022/1 | ErfXX; Erf 3806 Mdantsane unit 6 and Erf 756 Mdantsane West | Post 94 (1994 - 2014) | Peoples Housing Process (IRDP) | 2009-06-01 | 2012-03-12 | 16751614.65 | 16751614.65 |  | No | 0 |  | BCMM | 171 | 171 | 0 | 171 |  |  | Township Establishment | [18 empty] | ECDHS report suggest that there is a TR for this project, confirmations required in relation to beneficiary management. | There are three GP's under this name Soga i.e. First GP 1251/2019 located on parent ErfXXX consisting of 71 Erven; Second GP no. 404/2021 located on parent erf 3806 Mdantsane unit 6 & consist of 84 residential sites (no transfers & no houses, only informal settlements) and third GP no. C197/1992 located on parent Erf 756 Mdantsane West & consisting of 152 (there are houses contructed. Property Management to confirm the status of township register. | Updates on bulk & internal services corfimed | Township register not opened. Property Management await receipt of approved General plan and subdivisional approval under a cover of a memorandum from Develolpment Planning requesting registration of the township register. paragaph taken from muicipal report.
Eastern Cape | Buffalo City Metro | Buffalo City Metro |  |  |  | East London - Simanyene 93 subs (Phase 1) | C04050001/1 |  | Post 94 (1994 - 2014) | Progress Payment Housing Project |  |  | 8196275.2 | 8196275.2 |  | No | 0 |  | BCMM | 93 | 93 | 0 | 84 |  |  | Township Establishment
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Midlands |  |  | East London - Potsdam East/khayelitsha - 246 subs (Phase 1) | C04120001/1 |  | Post 94 (1994 - 2014) | Peoples Housing Process (IRDP) |  |  | 11055782.38 | 11055782.38 |  | No | 0 |  | ECDHS | 246 | 246 | 0 | 0 |  |  | Beneficiary Management | [18 empty] | ECDHS to confirm project location & property description & project status quo thereof. | ECDHS to confirm project location & property description & project status quo thereof. | The project is in Mdantsane, rectification of title deeds is required.
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Coastal |  |  | East London - Duncan Village Redevelopment BNG (Phase 1) | C05080001/1 |  | Post 94 (1994 - 2014) | Inner City Upgrading Project |  |  | 8760000 | 8760000 |  | No | 0 |  | ECDHS | 0 | 0 | 0 | 0 |  |  | Township Establishment | [15 empty] | Blocked |  |  | ECDHS to confirm project location & property description, because without those co ordinate it is impossible to determine the status of township establishment process. According to BEPP densities & land are the constraint affecting this project. | ECDHS to confirm project location & property description, because without those co ordinate it is impossible to determine the status of township establishment process. According to BEPP densities & land are the constraint affecting this project. | The project is not known by the ECDHS officials.
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Inland |  |  | KWT - Dimbaza Wooden Houses 134 subs (Phase 1) | C06010002/1 |  | Post 94 (1994 - 2014) | Peoples Housing Process (IRDP) | 2006-07-17 | 2009-07-17 | 1768368 | 1768368 |  | No | 0 |  | ECDHS | 134 | 118 | 0 | 5 |  |  | Township Establishment | [18 empty] | Township has been upgraded in terms of the land tenure (SPLUMA) for the whole Dimbaza township including pre 94 housing. | GP is confirmed & in place for Dimbaza area | Updates on bulk & internal services corfimed
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Inland |  |  | KWT - Dimbaza : Disabled People (Phase 1) | C06010006/1 |  | Post 94 (1994 - 2014) | Peoples Housing Process (IRDP) |  |  | 364342 | 364342 |  | No | 0 |  | ECDHS | 11 | 11 | 0 | 11 |  |  | Township Establishment | [18 empty] | Township has been upgraded in terms of the land tenure (SPLUMA) for the whole Dimbaza township including pre 94 housing. | GP is confirmed & in place for Dimbaza area | Updates on bulk & internal services corfimed
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Midlands |  |  | East London - Reeston Ph 3 - Disaster (796 subs) (Phase 1) | C06030001/1 | Erf 74450 East London registered under BCMM | Post 94 (1994 - 2014) | Progress Payment Housing Project | 2006-03-20 | 2009-03-31 | 31747171.04 | 31747171.04 |  | No | 0 |  | BCMM | 796 | 795 | 0 | 583 | 333 | 463 | Transfer Stage | [16 empty] | There are about only 463 outstanding transfers & 583 constructed houses to date out of 796 project yield & BCMM has about 43 un issued title deeds that needs to be handed over to the correct beneficiaries. | EC DoHS: To provide progress report on the balance of 463 outstanding transfers; exact no. of approved beneficiaries & total no of constructed houses. BCMM: To provide update on the remaining 43 un issued title deeds to be handed to the rightful beneficiaries. | Reeston Ph 3 Disaster; Reeston 2500 & Reeston Phase 3 stage 3 were approved via LEFTEA under one project name known as Reeston Phase 3 (Planning Report) in terms of LEFTEA in 2005. | The project is located on Erf 74450 East London registered under BCMM. There is a GP no. 1305/2012 in place & this GP has 488 erven. | Both ECDHS & BCMM to update progress relating to transfers in column W & X
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Coastal |  |  | East London - Second Creek 289 subs (Phase 1) | C09060001/1 - 2 |  | Post 94 (1994 - 2014) | Progress Payment Housing Project | 2013-11-01 | 2022-03-31 | 24589646.7 | 24372491.2 |  | No | 0 |  | BCMM | 289 | 265 | 265 | 265 |  |  | Township Establishment | [18 empty] | ECDHS to provide property description & project status quo report. | ECDHS to provide property description & project status quo report. | Updates on bulk & internal services corfimed | Project complete, there are 11 erven with constructed houses that need to be changed to new erven as they were relocated from old erves due to undevelopable sites.
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Midlands | -32.5439 | 27,3033 | East London - Potsdam Unit - P 2003 subs (services) | C09060004/1 - 6 | Erf 5295 Potsdam registered under BCMM | Post 94 (1994 - 2014) | Progress Payment Housing Project | 2015-04-01 | 27/07/2020 | 215580762.83 | 214324277.07 | Yes | Yes | 15088768.5 |  | BCMM | 2003 | 1740 | 131 | 1716 |  |  | Transfer Stage | [15 empty] | Active | It is not clear out of the 2 HSS project (Potsdam Unit P) which one should be the correct project name to use going forward | ECDoHS to confirm the correct HSS project name & also should provide the status quo report for further scrutiny. | Planning approval obtained in terms of LEFTEA between 2004 & 2006 on Erf 5295 Potsdam covering all Potsdam Unit P projects | There is a GP no. 343/2004 in place situated on Erf 5295 Potsdam registered under BCMM & consists of 2 528 erven covering all Potsdam Unit P projects. There are transfers that have taken place. | ECDHS report is silent on internal services & township register statuses. According 2023/24 BP R111 287,00 is budgeted for 67 properties.
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Midlands | -33.0144 | 27.8431 | East London - Reeston 2500 subs (- BCMM - services) | C09080002/1 - 44 |  | Post 94 (1994 - 2014) | Progress Payment Housing Project | 2009-07-23 | 2024-05-10 | 196816850.18 | 136794799.84 | Yes | Yes | 5577325 |  | BCMM | 2500 | 1130 | 0 | 3 | 1091 | 1409 | Transfer Stage | [15 empty] | Active | There are about only 1 409 outstanding transfers & 0 constructed houses to date out of 2 500 project yield & BCMM has about 111 un issued title deeds that needs to be handed over to the correct beneficiaries. | EC DoHS: To provide progress report on the balance of 1 409 outstanding transfers; exact no. of approved beneficiaries & total no of constructed houses. BCMM: To provide update on the 111 un issued title deeds to be handed to the rightful beneficiaries. | Reeston Ph 3 Disaster; Reeston 2500 & Reeston Phase 3 stage 3 were approved via LEFTEA under one project name known as Reeston Phase 3 (Planning Report) in terms of LEFTEA in 2005. | In Reeston about 8 GP's were identified; however ECDHS should assist in confiming where each GP is located within the project. | ECDHS report is silent on internal services & status of the township register. The PRM mentiions Reeston subs phase 2 (600) with HSS number 10110025/2 that hasn’t been observed on the assessed NDHS project list. According to the 2024/25 BP R83 050 for transfer of 50 properties.
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Midlands |  |  | East London - Thembelihle/Manyano 850 subs ( - Bandolite) | C10100001/1 |  | Post 94 (1994 - 2014) | Progress Payment Housing Project | 2014-10-24 | 2018-01-31 | 52585965.13 | 48139118.03 |  | No | 0 |  | ECDHS | 411 | 432 | 500 | 411 | 850 | 0 | Transfer Stage | [20 empty] | Updates on bulk & internal services confirmed & confirmation regarding transfers is required from Property Management & ECDHS.
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Midlands | -32.8782 | 27.2882 | East London - Thembelihle/Manyano 850 subs ( - Uphahla) | C10100001/2 |  | Post 94 (1994 - 2014) | Progress Payment Housing Project | 2014-11-12 | 2020-03-31 | 46952240.59 | 43506436.9 | Yes | Yes | 6305754 |  | ECDHS | 410 | 398 | 0 | 410 |  | 0 | Transfer Stage | [15 empty] | N/A |  |  |  |  | Both EDHS & BCMM to update information relating to column Y & Z. According to the 2024/25 BP R46 508,00 is budgeted for transfers of 28 properties bcz column Z indicate as if all transfers are complete, so confirmation is required.
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Midlands | -32.8404 | 27.2265 | East London - Mdantsne Zone 18 cc 1500 subs (Phase 1) | C10100004/1 | Erf 2106 Mdantsane CC registered under XXXXX | Post 94 (1994 - 2014) | Progress Payment Housing Project | 2023-04-23 | 2024-04-27 | 551523 | 551523 | Yes | Yes | 46986800 |  | BCMM | 1500 | 1315 | 1000 | 125 |  |  | Township Establishment | Yes | [13 empty] | Yes | Active | The received municipal report isnt clear on which milestone this project is at i.e. township establishment milestones & update on approved beneficiaries is required. | EC DoHS: To provide update on the number of approved beneficiaries including other activities such as installation of bulk and reticulation services. | Mdantsane Zone CC 427 & Mdantsane Zone 18 cc 1 500 is one project area that has Town Planning approval & GP in place. To date installation of services is being undertaken. | There is a GP no. C8/1986 in place situated on Erf 2106 Mdantsane CC registered under BCMM & consists of XXX erven. | The PRM mentions Mdantsane Zone 18 Phase 2 consisting of 500 with no HSS number while NDHS mentioned Mdantsane Zone 18cc consisting of 1500 subs (C1010004/1). Going forward it is recommended that all projects should have a clear dedicated number. The 2024/25 BP R728 000 budgeted for transfers of 240 properties, target is unrealistic. | On this project internal services were done by BCMM, the next phase was given to H D A for the implementation & construction of top structure housing and the balance of internal services. Currently H D A contractor is on site proceeding with the works.
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Coastal | -33.1226 | 27.3637 | East London - Duncan Village DVRI 323 (Phase 1) | C10110025/1 |  | Post 94 (1994 - 2014) | Progress Payment Housing Project | 2011-11-10 | 2023-03-31 | 14864988.59 | 14864988.59 | Yes | Yes | 4674915 |  | BCMM | 192 | 340 | 192 | 192 |  |  | Township Establishment | [14 empty] | Yes | Blocked |  |  | ECDHS to confirm project location & property description, because without those co ordinate it is impossible to determine the status of township establishment process. | ECDHS to confirm project location & property description, because without those co ordinate it is impossible to determine the status of township establishment process. | The project is being implemented & within this project there is a phase for military veterans 30. Updates on bulk & internal services confirmed. According to 2024/25 BP R24 915 is budgeted for transfers of 15 properties. | Project complete, there are 131 sites that could not be constructed due to land invasion hence there are only 132 houses built & project reduced from the original yield of 323. Deregistration of certain beneficiaries is required.
Eastern Cape | Buffalo City Metro | Buffalo City Metro |  |  |  | East London - BCM - Emergency Housing 988 (Phase 1) | C11050001/1 - 2 |  | Post 94 (1994 - 2014) | Progress Payment Housing Project | 2011-04-20 | 2018-09-30 | 100194114.31 | 97824075.49 |  | No | 0 |  | ECDHS | 988 | 988 | 0 | 985 |  |  | Township Establishment | [20 empty] | The project is referred back to BCMM for township establishment milestones. Project is unknown.
Eastern Cape | Buffalo City Metro | Buffalo City Metro |  |  |  | East London - Byletts (Phase 1) | C11050005/1 |  | Post 94 (1994 - 2014) | Peoples Housing Process (Rural) | 2013-11-27 | 2014-02-26 | 85000 | 85000 |  | No | 0 |  | ECDHS | 0 | 0 | 0 | 0 |  |  | Township Establishment | [20 empty] | The project is not known at all by ECDHS. Project unknown
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Inland |  |  | KWT - Dimbaza Wooden Houses - Rectification (Phase 1) | C11060022/1 |  | Post 94 (1994 - 2014) | Progress Payment Housing Project | 2013-08-14 | 2018-12-12 | 11106264.12 | 11106264.12 |  | No | 0 |  | ECDHS | 0 | 0 | 0 | 0 |  |  | Township Establishment | [18 empty] | Township has been upgraded in terms of the land tenure (SPLUMA) for the whole Dimbaza township including pre 94 housing. | GP is confirmed for the whole area of Dimbaza | Updates on bulk & internal services confirmed
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Midlands |  |  | East London - Reeston 6 subs (Phase 1) | C12030003/1 |  | Post 94 (1994 - 2014) | Progress Payment Housing Project | 2012-11-23 | 2013-03-23 | 435714.06 | 435714.06 |  | No | 0 |  | ECDHS | 6 | 0 | 0 | 0 |  |  | Township Establishment | [20 empty] | Recently picked up from HSS by Ayanda
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Coastal |  |  | East London - Ndancama 508 subs (Phase 1) | C12060007/1 | Erf74943 East London registered under BCMM | Post 94 (1994 - 2014) | Progress Payment Housing Project | 2018-06-15 | 2023-03-31 | 58052914.12 | 48199533.7 | Yes | No | 7000000 | USDG & HSDG | BCMM | 508 | 508 | 508 | 505 |  | 500 | Township Establishment | [14 empty] | Yes | Blocked | Following confirmations are required i.e.the exact no. of approved beneficiaries; no. of units constructed to date & status quo on township estblaishment milestones. | EC DoHS: to confirm the exact no. of approved beneficiaries cz HSS reflects only 504 approved beneficiaries & no. of units constructed on the ground; to date 505 constructed houses against 508 (project yield). BCMM: To confirm the status of township establishment milestones, especially town planning activities. | GP 384/2028 approved, so land use to confirm the status of issuing complience certificate. | The project is located on Erf74943 East London registered under BCMM & GP 374/2018 is in place. Engineering & Land Use to confirm the project status. | Updates on bulk & internal services confirmed | The project is stalled due to illigal occupation of 18 houses. This project is clustered with Fynbos 1 anad Fynbos 2 as one project. All three project share budget, & contract, also they were all implemented as one cluster project with one contractor appointment.
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Midlands |  |  | East London - Mathemba Vuso 75 USDG (Phase 1) | C12060011/1 | Erf 11521; 11524 & 11526 Mdantsane unit 3 registered under BCMM | Post 94 (1994 - 2014) | Progress Payment Housing Project |  | To Be Determined | 20000000 | 0 |  | No | 0 |  | BCMM | 75 | 59 | 0 | 0 |  |  | Township Establishment | [16 empty] | The received municipal report isnt clear on which milestone this project is at i.e. township establishment milestones & update on approved beneficiaries is required. | EC DoHS: To provide update on the number of approved beneficiaries including other activities such as installation of bulk and reticulation services. BCMM: To provide a clear update regarding the status of the township establishment milestones i.e. town planning approvals and opening of township register. |  | There is a GP no.4044/2006 in place located in three parent erven i.e. Erf 11521; 11524 & 11526 Mdantsane unit 3 registered under BCMM. The GP has a total of 59 sites (no houses built to date, but there are informal settlements). | This project is not known by ECDHS team | This project form part of the Mndantsane Cluster 2, which consists of 8 areas included in one budget as a cluster project. The previous contractor for this Cluster project was teminated in 2018 due to poor perfomance. H D A is implementing this project for internal services & top structure houses.
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Midlands |  |  | East London - Francis Mei 70 USDG (Phase 1) | C12060012/1 | Erven 4386 - 4389 Mdantsane unit 5 registered under BCMM | Post 94 (1994 - 2014) | Progress Payment Housing Project | not yet | to be determined | 20000000 | 0 |  | No | 0 |  | BCMM | 70 | 68 | 0 | 0 |  |  | Township Establishment | [16 empty] | The received municipal report isnt clear on which milestone this project is at i.e. township establishment milestones & update on approved beneficiaries is required. | EC DoHS: To provide update on the number of approved beneficiaries including other activities such as installation of bulk and reticulation services. BCMM: To provide a clear update regarding the status of the township establishment milestones i.e. town planning approvals and opening of township register. |  | There is a GP no.4052/2006 in place & is consisting of 71 erven & is located on parent property erven 4386 - 4389 Mdantsane unit 5 registered under BCMM, therefore infrastructure unit to confirm availability of services. The GP for this project area is in 3 parts & one side of the part looks like construction activities are underway while the other has no activities (possible relocations required). | This is one of the infill projects implemented by BCMM | This project form part of the Mndantsane Cluster 2, which consists of 8 areas included in one budget as a cluster project. The previous contractor for this Cluster project was teminated in 2018 due to poor perfomance. H D A is implementing this project for internal services & top structure houses.
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Coastal |  |  | East London - Fynbos Ph 1 - 577 subs (Phase 1) | C12070001/1 | Erf 73682 East London registered under BCMM | Post 94 (1994 - 2014) | Progress Payment Housing Project | 2019-11-25 | 2023-03-31 | 65938054.03 | 47389600.29 | Yes | Yes | 7000000 | USDG & HSDG | BCMM | 577 | 555 | 577 | 554 | 0 | 577 | Beneficiary Management | [14 empty] | Yes | Blocked | Following confirmations are required i.e.the exact no. of approved beneficiaries; no. of units constructed to date & status quo on township estblaishment milestones. | EC DoHS: to confirm the exact no. of approved beneficiaries cz HSS reflects only 557 approved beneficiaries & no. of units constructed on the ground; to date 325 constructed houses against 577 (project yield). BCMM: To confirm the status of township establishment milestones, especially town planning activities. | GP 726/2014 is in place & the TR has recently been opened, therefore expiry date scheduled for April is N/A. | GP 726/2014 is in place & the TR has recently been opened, therefore expiry date scheduled for April is N/A. | It is recommended that beneficiary verification be undertaken for this project | The project is stalled due to illigal occupation of 27 houses. Also shack dwellers who refused to be relocated to an alternative site.
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Coastal |  |  | East London - Fynbos Ph 2- 214 subs (Phase 1) | C12070002/1 | Erf 74232 East London registered under BCMM | Post 94 (1994 - 2014) | Progress Payment Housing Project | 2019-11-25 | 2021-12-31 | 24455361.46 | 0 | Yes | No | 7000000 | USDG & HSDG | BCMM | 214 | 211 | 114 | 0 | 0 | 214 | Beneficiary Management | [14 empty] | Yes | Blocked | Following confirmations are required i.e.the exact no. of approved beneficiaries; no. of units constructed to date & status quo on township estblaishment milestones. | EC DoHS: to confirm the exact no. of approved beneficiaries cz HSS reflects only 211 approved beneficiaries & no. of units constructed on the ground; to date 0 houses constructed against 214 (project yield). BCMM: To confirm the status of township establishment milestones, especially town planning activities. | GP 726/2014 is in place & the TR has recently been opened, therefore expiry date scheduled for April is N/A. Contradictions between HSS records (214) & ECDHS report (500) observed especially on the no. of units. | The project is located on Erf 74232 East London registered under BCMM and GP 297/2014 is in place. The TR has recently been opened, therefore expiry date scheduled for April is N/A. Contradictions between HSS records (214) & ECDHS report (500) observed especially on the no. of units, ECDHS to provide project status quo. | Mr Fihla to provide updates on TR & Transfer | The project is stalled due to illigal occupation of 112 incomplete houses, who were meant to be compeleted and handed over to the rightful benefitaries that are currently residing on TRU due to relocation of shack dwellers who are benefitiaries.
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Midlands |  |  | East London - Gwentshe 25 subs USDG (Phase 1) | C12070005/1 | Erf 9626 Mdantsane unit 3 registered under BCMM | Post 94 (1994 - 2014) | Progress Payment Housing Project |  |  | 20000000 | 0 |  | No | 0 |  | BCMM | 25 | 21 | 0 | 0 |  |  | Township Establishment | [15 empty] | Blocked | The received municipal report isnt clear on which milestone this project is at i.e. township establishment milestones & update on approved beneficiaries is required. | EC DoHS: To provide update on the number of approved beneficiaries including other activities such as installation of bulk and reticulation services. BCMM: To provide a clear update regarding the status of the township establishment milestones i.e. town planning approvals and opening of township register. | The project is affected environmental sensitivite (wetland) & town planning approveal was once obtained subject to floodine determination.Alternative land is required & planning has been undertake on the alternative land, however there are social challenges / disputes. | There is no GP, however it be noted that the subject area is located on property Erf 9626 Mdantsane unit 3 registered under BCMM. The project is affected by environmental sensitive (wetland) & town planning approval was once obtained subject to floodine determination.Alternative land is required & planning has been undertake on the alternative land, however there are social challenges / disputes. | The project is hindered by environmental constraints, therefore it cannot attain any further township establishment milestones. | This project form part of the Mndantsane Cluster 2, which consists of 8 areas included in one budget as a cluster project. The previous contractor for this Cluster project was teminated in 2018 due to poor perfomance. H D A is implementing this project for internal services & top structure houses.
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Midlands |  |  | East London - Mahlangu Village 91 subs USDG (Phase 1) | C12070006/1 | Erf 3679 Mdantsane N registered under BCMM | Post 94 (1994 - 2014) | Progress Payment Housing Project |  |  | 20000000 | 0 |  | No | 0 |  | BCMM | 91 | 90 | 0 | 0 |  |  | Township Establishment | [16 empty] | The received municipal report isnt clear on which milestone this project is at i.e. township establishment milestones & update on approved beneficiaries is required. | EC DoHS: To provide update on the number of approved beneficiaries including other activities such as installation of bulk and reticulation services. BCMM: To provide a clear update regarding the status of the township establishment milestones i.e. town planning approvals and opening of township register. |  | There is a GP no. 5207/2007 is in place located on Erf 3679 Mdantsane N registered under BCMM & consists of 91 Erven (no transfres & no houses only informal settlements).. | This project is not known by ECDHS team | This project form part of the Mndantsane Cluster 2, which consists of 8 areas included in one budget as a cluster project. The previous contractor for this Cluster project was teminated in 2018 due to poor perfomance. H D A is implementing this project for internal services & top structure houses.
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Inland |  |  | KWT - Ilitha Wooden Houses 300 subs (Phase 1) | C13020021/1 |  | Post 94 (1994 - 2014) | Progress Payment Housing Project | 2014-10-02 | 2019-11-30 | 23881804.04 | 11890065.02 |  | No | 0 |  | ECDHS | 262 | 181 | 0 | 130 |  |  | Township Establishment | [18 empty] | ECDHS to provide property description, however according to planning the GP are in place for the whole project area. Planning approval obtained around 2005/6 fy. | GP is in place & is confirmed for this project area. | Updates on bulk & internal services confirmed
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Midlands |  |  | East London - Reeston Phase 3 Stage 3 - 1137 subs ( - Top Structures) | C13020023/1 - 2 |  | Post 94 (1994 - 2014) | Progress Payment Housing Project | 2014-07-23 | 2019-12-31 | 351361931.84 | 135729192.79 |  | Yes | 100000 |  | BCMM | 1137 | 933 | 933 | 935 |  |  | Township Establishment | [14 empty] | Yes | Blocked |  |  | Reeston Ph 3 Disaster; Reeston 2500 & Reeston Phase 3 stage 3 were approved via LEFTEA under one project name known as Reeston Phase 3 (Planning Report) in terms of LEFTEA in 2005. Property Management to report / confirm the status of opening TR for this project. | Reeston Ph 3 Disaster; Reeston 2500 & Reeston Phase 3 stage 3 were approved via LEFTEA under one project name known as Reeston Phase 3 (Planning Report) in terms of LEFTEA in 2005. Property Management to report / confirm the status of opening TR for this project. | Updates on bulk & internal services confirmed | This project had a yeild of 1137, contractor was appointed in 2014 for the construction of both internal services and top structure houses. Out of 1137 sites, 66 site could not be constructed due to land that was to be transfered from Dertment of Agriculture, Land Reform and Rural Development to BCMM. Contractor therefore completed 935 site, on internal services and top structure houses, handedover to righful benefiticiaries. The project was then closed in 2017, pending the resolution of the Land issue for 66 sites.
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Coastal | -32.929 | 27.6746 | East London - Needs Camp 1072 subs (Phase 1) | C13070007/1 - 3 | Erf 1444 Needscamp registered under BCMM | Post 94 (1994 - 2014) | Peoples Housing Process (IRDP) | 2014-02-10 | 2016-07-31 | 71620730.58 | 70881940.34 | Yes | Yes | 10506591.5 |  | ECDHS | 1072 | 1051 | 1041 | 1036 |  |  | Township Establishment | [15 empty] | Active |  |  | There is a GP approval for Needscamp GP No.7307/1992, so land use Mng to confirm the status of compliance certificate issuing. ECHDS to give more info on status quo | The project is located on Erf 1444 Needscamp registered under BCMM & GP GP No.7307/1992 is in place. Engineering & Land use Mng to confirm the status of the project. ECHDS to give more info on status quo | According to this report the project has no GP, yet BCMM land survey confirmed approved GP. Contradiction is notedbetween BCMM & ECDHS. ECDHS confirmed that this project is a rural project. Confirmation to be obtained from Mjo.
Eastern Cape | Buffalo City Metro | Buffalo City Metro |  |  |  | East London - Nelson Mandela 102 subs (Phase 1) | C13090001/1 |  | Post 94 (1994 - 2014) | Peoples Housing Process (IRDP) | 2014-08-13 | 2015-04-13 | 50490 | 50490 |  | No | 0 |  | BCMM | 102 | 3 | 0 | 0 |  |  | Township Establishment | [20 empty] | No HSS number for the project on the PRM & HDA to appoint the service provider for undertaking the design of internal services. ECDHS will check further the project & thereafter come back with updates. | The HDID report indicate that SPLUMA requires extension & detailed design form part of planned activities.
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Midlands |  |  | East London - Potsdam( North Kanana) 924 subs USDG (Phase 1) | C14070004/1 | Erf 8671 Potsdam which is originating from Erf351 (Parent Property) registered under XXXXXX. | Post 94 (1994 - 2014) | Progress Payment Housing Project |  |  | 0 | 0 |  | No | 0 |  | BCMM | 924 | 447 | 0 | 0 |  |  | Township Establishment | [18 empty] | Planning approval obtained in terms of LEFTEA between 2004 & 2006 (Erf 351) owned by BCMM. | The project is seating on the parent Erf 8671 Potsdam which is originating from Erf351. There is a GP no. 3070/2006 consisting of 1 009 erven. No transfers undertaken thus far & there are no houses built to date. There are only informal structures on site. | The project has no bulk & internal services, currently internal services are at a design stage. | HDID report indicate that the project size has been reduced from 928 to 828 & that consultant is preparing tender document for the bulk sewer oufall.
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Coastal | -32.935 | 27.4615 | East London - Amalinda Co-op 100 subs (Phase 1) | C14090001/1 | Erf 56346 & 56347 registered XXX | Post 94 (1994 - 2014) | Progress Payment Housing Project | 2021-01-06 | 2024-04-10 | 109988567 | 0 | Yes | Yes | 11412275 |  | BCMM / ECDHS | 100 | 100 | 100 | 80 |  |  | Township Establishment | [7 empty] | GP No.213/2002 | [6 empty] | Yes | Active |  |  | GP 213/2002 is in place, so land use planning to confirm the status of Compliance Certificate. | The project is located on Erf 56346 & 56347 registered XXX & GP 363/2005 in place. Land survey to confirm the correct GP no 213/2002 cz there are two GP number prior to further required updates from engineering & land use planning. | Bulk services are confirmed, however the BP indicate that internal services are currently being installed. According to BP a total of R235 050 is budgeted for transfers of 150 properties, the target for transsfers is unrealistic. | HDID report confirm that internal services are in place, therefore update on compliance certificate is requied.
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Midlands |  |  | East London - Mdantsane Infill Area 1613 ( - 1459 subs) &(-154 Subs) | C14100005/1 - 2 |  | Post 94 (1994 - 2014) | Progress Payment Housing Project | 2014-10-02 | 2023-03-31 | 190445093.44 | 91050757.86 |  | No | 0 |  | BCMM | 1613 | 1557 | 0 | 835 |  |  | Township Establishment | [18 empty] | ECDHS to provide property description & TE status quo report. | ECDHS to provide property description & TE status quo report. | Updates on bulk & internal services confirmed | According to HDID report this project covers Masibambane, Masibulele, Ilinge, Velwano & Dacawa. Contractor is on site constrructing houses on the last part of the project in Masibulele.
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Midlands |  |  | East London - Mdantsane 427 - 50 subs Rect. (Phase 1) | C15060002/1 |  | Post 2014 (2015 - 2018) | Peoples Housing Process (IRDP) | 2015-06-08 | 2023-02-22 | 6134507.5 | 5465684.35 |  | No | 0 |  | ECDHS | 18 | 0 | 0 | 18 |  |  | Township Establishment | [18 empty] | ECDHS to provide property description & TE status quo report. | There is no GP for this project, therefore ECDHS to provide property description & TE status quo report. | Initially this project was earmarked for rectification of 50 houses; however due to the findings 18 houses were rectified. This project located in one place, it is part of Mdantsne Zone CC - 427 (C97120014/1) above.
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Midlands |  |  | East London - Winnie Mandela 300 subs (Phase) | C15080002/1 | Erf 11367 (Winnie Madela 300) & Erf 11363 (Vukani without word park) Mdantsane unit 2 which are registered under BCMM. | Post 2014 (2015 - 2018) | Progress Payment Housing Project |  |  | 20000000 | 0 |  | No | 0 |  | HDAA | 300 | 213 | 289 | 0 |  |  | Township Establishment | [18 empty] | ECDHS to provide property description and status report on TE processes. | There is a GP no.5174/2007 in place located over Erf 11367 (Winnie Madela 300) & Erf 11363 (Vukani without word park) Mdantsane unit 2 which are registered under BCMM. | The project is a infill & at this stage it is at planning stage | This project form part of the Mndantsane Cluster 2, which consists of 8 areas included in one budget as a cluster project. The previous contractor for this Cluster project was teminated in 2018 due to poor perfomance. H D A is implementing this project for internal services & top structure houses.
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Inland |  |  | KWT - Ilitha 177 subs (Phase) | C15090001/1 |  | Post 2014 (2015 - 2018) | Progress Payment Housing Project |  |  | 0 | 0 |  | No | 0 |  | BCMM | 177 | 146 | 0 | 0 |  |  | Township Establishment | [18 empty] | ECDHS to provide property description, however according to planning the GP are in place for the whole project area. Planning approval obtained around 2005/6 fy. | GP is in place & is confirmed for this project area. | Updates on bulk & internal services confirmed
Eastern Cape | Buffalo City Metro | Buffalo City Metro |  |  |  | East London - Military Veterans 14 subs (Phase) | C15100003/1 |  | Post 2014 (2015 - 2018) | Progress Payment Housing Project |  |  | 0 | 0 |  | No | 0 |  | ECDHS | 14 | 6 | 0 | 0 |  |  | Township Establishment | [20 empty] | ECDHS to confirm with other provincial colleauge regarding the project status quo.
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Inland |  |  | Berlin - Dongwe 500 (Phase) | C17070024/1 |  | Post 2014 (2015 - 2018) | Progress Payment Housing Project |  |  | 0 | 0 |  | No | 0 |  | ECDHS | 500 | 0 | 0 | 0 | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | ECHDS to provide property description for the project & status quo thereof | Rural project therefore certain milestones are not applicsable.
Eastern Cape | Buffalo City Metro | Buffalo City Metro |  |  |  | East London - Military Veterans 179 (Phase) | C17070026/1 |  | Post 2014 (2015 - 2018) | Progress Payment Housing Project | Not Yet | Not Yet | 0 | 0 | Yes | Yes | 3000000 |  | HDAA | 179 | 91 | 0 | 0 |  |  | Township Establishment | No | [7 empty] | Yes | No | [5 empty] | Active |  |  |  |  | ECDHS to confirm with other provincial colleauge regarding the project status quo. | The project is at procurement stage for the appointemet of a professional team to design and construction supervision. Project is being implemented by Housing Development Agency (HDA) for BCMM.
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Inland | -32.9344 | 27.6435 | KWT - Breidbach 560 Sites (Phase) | C17080007/1 |  | Post 2014 (2015 - 2018) | Progress Payment Housing Project |  |  | 0 | 0 | Yes | Yes | 18353660 |  | ECDHS | 560 | 0 | 0 | 0 |  |  | Township Establishment | [16 empty] | It is not clear out of the 2 HSS project (Breidbach) which one should be the correct project name to use going forward. | ECDoHS to confirm the correct HSS project name & also should provide the status quo report for further scrutiny. | ECDHS to provide property desription & status quo report thereof, for this project. | ECDHS to provide property desription & status quo report thereof, for this project. | ECDHS report indicate that the project has GP in place & bulk services are underway (in progress). The project must be reffered back to BCMM. According to 2024/25 BP R470 000 is budgeted for transfers of 300 properties, this target is unrealistic.
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Midlands |  |  | East London - Mdantsane Cluster 2 - 344 subs (Phase) | C17080023/1 |  | Post 2014 (2015 - 2018) | Progress Payment Housing Project | 2018-06-12 | 2023-03-31 | 39111212.56 | 13405662.86 |  | No | 0 |  | BCMM | 344 | 341 | 0 | 0 |  |  | Township Establishment | [18 empty] | ECDHS to provide property description & TE status quo report. | ECDHS to provide property description & TE status quo report. | This project is located in different pockets within Mdantsane i.e. some pockets have internal services & others don’t therefore BCMM to confirm project status quo regarding internal services. | Confirmation of correct project yield is required whether is 344 or 366 from Project managers.
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Midlands |  |  | East London - Potsdam Ikhwezi Block 1- 656 subs - 203 subs (Phase) | C18080005/1 - 2 | Erf 7979 Potsdam registered under BCMM | Post 2014 (2015 - 2018) | IRDP - Housing Construction Project Linked | 2024-11-07 | 2026-11-09 | 173903843.92 | 0 | Yes | No | 36000000 | ISUPG & HSDG | BCMM | 656 | 203 | 656 | 0 |  |  | Township Establishment | Yes | [17 empty] | Observed GP 468/2005 of subdivisions of ERF 7979 Potsdam owned by BCMM is in place. Approval looks like it covers Ikhwezi Block 1 (656 subs) & Khwezi Block 203 subs hence in this report both projects are considered as one. | There is a GP no. 468/2005 in place located on parent Erf 7979 Potsdam registered under BCMM. This GP consists of 675 erven & the approval looks like it covers Ikhwezi Block 1 (656 subs) & Khwezi Block 203 subs hence in this report both projects are considered as one. | The ECDHS report suggest that this project is a rural, yet National HSS indicate that the project is IRDP, hence contradiction on GP status. | Currently the project is under construction for both houses and internal services. The contructor has been appointed to construct both components on 656 sites. Previous contractor was terminated now a replecement contract has been appointed.Possibly the project may be duplicated.
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Midlands |  |  | East London - Potsdam Village 500 (Phase) | C18080006/1 | Erf 2097 Potsdam Yellowoods & Erf 1338 Potsdam Yellowoods | Post 2014 (2015 - 2018) | IRDP - Housing Construction Project Linked | 28/04/2019 | 30/07/2023 | 81066485.18 | 0 | Yes | Yes | 8100000 | HSDG & ISUP | ECDHS | 500 | 0 | 0 | 500 |  |  | Township Establishment | [19 empty] | There are two GP's under this project area i.e. GP no. 2836/2005 located on 2097 Potsdam Yellowoods & consists of 919 Erven. It looks like there are no transfers, yet the picture suggest that there are houses constructed within theis GP. The second GP no. 2822/2005 located on Erf 1338 Potsdam Yellowoods consisting of 741 Erven & on this one there are houses constructed yet it looks like there are no transfers yet. | The project is a rural, therefore GP's & other milestones such as townhip regiser are not applicable. Contradiction between BCMM & ECDHS identified (Rural / Urban). | 500 houses have been constructed, completed and handed over to rightful benefitiaries including rainwater tanks & plumbing for rainwater harvesting. This is rural project, implemented on an established rural village for destitute benefitiaries who can not affort to build a formal structure in there rural sites. Project to go on tender for the next phase of 300 houses.
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Coastal |  |  | East London - Cambridge West Cnip 285 - 275 units (Phase) | C18080008/1 | Erf 78780 East London registered under BCMM | Post 2014 (2015 - 2018) | Progress Payment Housing Project | 2022-02-22 | 2026-03-31 | 40007110 | 0 |  | No | 0 |  | BCMM | 275 | 86 | 0 | 0 |  |  | Township Establishment | Yes | [8 empty] | In Progress | [6 empty] | It is not clear out of the 4 HSS project (Cambridge) which one should be the correct project name to use going forward | ECDoHS to confirm the correct HSS project name & also should provide the status quo report for further scrutiny. | There is a GP in place GP 1352 of 2017 & planning approval obtained on 09 Oct 2015 & extension of the planning approval was granted on 7 Sept 2020 for addional +- 2 yrs to allow for installation of internal services. | The project is located on Erf 78780 East London registered under BCMM & has a GP 1352/2017 in place. The extension of the planning approval was granted on 7 Sept 2020 for addional +- 2 yrs to allow for installation of internal services. Engineering & Land Use to provide project status quo. | The report is silent about internal services, hence confirmation is still required. | Currently the project is under construction for both houses and internal services. The contructor has been appointed to construct both components on 275 sites.
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Inland |  |  | KWT - Erf 2700 Housing Project - 785 (Phase) | C18080009/1 |  | Post 2014 (2015 - 2018) | Progress Payment Housing Project |  |  | 0 | 0 |  | No | 0 |  | ECDHS | 785 | 0 | 0 | 0 |  |  | Township Establishment | [18 empty] | ECDHS provincial to confirm the status of this project & location thereof. The identified Erf 2700 is located in King Williams Town. | ECDHS provincial to confirm the status of this project & location thereof. The identified Erf 2700 is located in King Williams Town. | Project is not known by officials, therefore it should be reffered back to BCMM.
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Midlands |  |  | East London - Winnie 164 subs (Phase) | C18080018/1 | Erf 1083 & extended to Erf 1111 Mdantsane unit 4 registered under BCMM (no GP. Erven 877 BCMM owned); 1081 (BCMM owned) & 1082 (privatly owned) in Mdantsane unit 4 | Post 2014 (2015 - 2018) | Progress Payment Housing Project |  |  | 0 | 0 |  | No | 0 |  | ECDHS | 164 | 0 | 0 | 0 |  |  | Township Establishment | [18 empty] | ECDHS to provide property description and status report on TE processes. | Under the informal settlement there are Winnie A, B & C. Winnie A located on Erf 1083 & extended to Erf 1111 Mdantsane unit 4 registered under BCMM (no GP). Winnie B located on Erven 877 BCMM owned); 1081 (BCMM owned) & 1082 (privatly owned) in Mdantsane unit 4, to date there are no GP's in place. | To date no GP for this project.
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Inland |  |  | KWT - Destitute 2 subs (Phase) | C18120001/1 |  | Post 2014 (2015 - 2018) | Progress Payment Housing Project | 2014-05-06 | 2019-03-31 | 291600 | 249840 |  | No | 0 |  | ECDHS | 2 | 2 | 0 | 0 |  |  | Township Establishment | [18 empty] | ECDHS provincial to confirm the status of this project & location thereof. | ECDHS provincial to confirm the status of this project & location thereof. | Project is not known by officials & it consists of only two houses, therefore it may be removed from Master plan.
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Coastal |  |  | East London - Duncan Village C-section 1200 subs (Phase) | C18120004/1 |  | Post 2014 (2015 - 2018) | IRDP - Housing Construction Project Linked |  |  | 0 | 0 |  | No | 0 |  | ECDHS | 1200 | 0 | 0 | 0 |  |  | Township Establishment | [15 empty] | Blocked |  |  | The granted town planning extension obtained in 2015 is expiring in March 2024 (Erf 30470). Temporal Relocation Area (TRA) is required & as a result the survey hasn't taken place & possible the new application will have to be re submitted in terms of SPLUMA. | The granted town planning extension obtained in 2015 is expiring in March 2024 (Erf 30470). Temporal Relocation Area (TRA) is required & as a result the survey hasn't taken place & possible the new application will have to be re submitted in terms of SPLUMA. | The project is hindered by the required Temporal Relocation Area (TRA) constraints, therefore it cannot attain any further township establishment milestones.
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Inland | -32.7909 | 27.7432 | KWT - Ginsberg 510 subs (Phase) | C18120005/1 |  | Post 2014 (2015 - 2018) | Progress Payment Housing Project |  |  | 0 | 0 | Yes | Yes | 2645247 |  | ECDHS | 510 | 0 | 0 | 0 |  |  | Township Establishment | [15 empty] | Active |  |  | Services havent yet been installed & there is a problem with sewer i.e. Bulk Infratructure. Ayanda Damane is the contact person in BCMM for inland, he is from BCMM Sanitation. | ECDHS to provide property description and status report on TE processes. GP is subject to confirmation. | Bulk is availabke & the project has no internal services
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Midlands |  |  | East London - Potsdam Ikhwezi Block 1- 203 subs (Phase) | C19010002/1 - 2 | ERF 7979 Potsdam owned by BCMM is in place | New (2019 - To Date) | Progress Payment Housing Project | 2019-12-10 | 2023-03-31 | 28129726.24 | 7267815.7 |  | No | 0 |  | BCMM | 203 | 203 | 0 | 0 |  |  | Township Establishment | [18 empty] | Observed GP 468/2005 of subdivisions of ERF 7979 Potsdam owned by BCMM is in place. Approval looks like it covers Ikhwezi Block 1 (656 subs) & Khwezi Block 203 subs hence in this report both projects are considered as one. | Observed GP 468/2005 of subdivisions of ERF 7979 Potsdam owned by BCMM is in place. Approval looks like it covers Ikhwezi Block 1 (656 subs) & Khwezi Block 203 subs hence in this report both projects are considered as one. | Refer project back to BCMM (New Project). | Currently the project is under construction for both houses and internal services. The contructor has been appointed to construct both components on 656 sites. Previous contractor was terminated now a replecement contract has been appointed. This is the same project in raw 73.Possibly project may be duplicated.
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Midlands |  |  | East London Reeston Mpcc (Phase) | C19080001/1 |  | New (2019 - To Date) | Project Linked Housing Project on Existing Sites |  |  | 0 | 0 |  | No | 0 |  | BCMM | 0 | 0 | 0 | 0 |  |  | Township Establishment | [18 empty] | ECDHS to provide property description & project status quo report. | ECDHS to provide property description & project status quo report. | Refer project back to BCMM; however PRM indicate intervention as social & economic facilitues, possibly this project may be for other land use & not residential purposes.
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Coastal |  |  | East London - Amalinda Forest 1184 subs (Phase) | C19080084/1 | Erf 644 East London registered under BCMM | New (2019 - To Date) | Progress Payment Housing Project |  |  | 0 | 0 |  | No | 0 |  | BCMM | 1184 | 0 | 0 | 0 |  |  | Township Establishment | [15 empty] | Blocked |  |  | Feasibility study done & was approved, funding is required for acquisition of private land parcels on some portions affecting this project. | The project is located on Erf 644 East London registered under BCMM & there is no township register in place. Feasibility study done & was approved, funding is required for acquisition of private land parcels on some portions affecting this project. | The project is hindered by land constraints, therefore it cannot attain any further township establishment milestones.
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Midlands |  |  | East London - Andrew Mlangeni 89 subs (Phase) | C19080090/1 | Erf 4378 Mdantsane unit 2 ownership still subject to confirmation. | New (2019 - To Date) | Progress Payment Housing Project |  |  | 0 | 0 |  | No | 0 |  | BCMM | 89 | 0 | 0 | 0 |  |  | Township Establishment | [19 empty] | The project has no GP in place & is located on Erf 4378 Mdantsane unit 2 ownership still subject to confirmation. | Refer project back to BCMM
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Inland |  |  | KWT - Bhisho-Tyutyu 465 subs (Phase) | C19080099/1 |  | New (2019 - To Date) | Progress Payment Housing Project |  |  | 0 | 0 |  | No | 0 |  | BCMM | 465 | 0 | 0 | 0 |  |  | Township Establishment | [18 empty] | ECDHS to confirm property description for this project to enable us to determine the TE status. | ECDHS to confirm property description for this project to enable us to determine the TE status. | Refer project back to BCMM
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Midlands |  |  | East London - Barcelona 37 subs (Phase) | C19080101/1 | Erf 9666 Mdantsane unit 3 registered under BCMM | New (2019 - To Date) | Progress Payment Housing Project |  |  | 0 | 0 |  | No | 0 |  | BCMM | 37 | 0 | 0 | 0 |  |  | Township Establishment | [19 empty] | The project has no GP in place & is located on Erf 9666 Mdantsane unit 3 registered under BCMM. | Refer project back to BCMM
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Coastal |  |  | East London - Cambridge 1341 subs (Phase) | C19080102/1 |  | New (2019 - To Date) | Progress Payment Housing Project |  |  | 0 | 0 |  | No | 0 |  | BCMM | 1347 | 0 | 0 | 0 |  |  | Township Establishment | [16 empty] | It is not clear out of the 4 HSS project (Cambridge) which one should be the correct project name to use going forward | ECDoHS to confirm the correct HSS project name & also should provide the status quo report for further scrutiny. | ECDHS to give status / progress report on this project in relation to milestones. | ECDHS to give status / progress report on this project in relation to milestones. | Refer project back to BCMM
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Coastal |  |  | East London - Duncan Village Gesini subs (Phase) | C19080106/1 |  | New (2019 - To Date) | Progress Payment Housing Project |  |  | 0 | 0 |  | No | 0 |  | BCMM | 0 | 0 | 0 | 0 |  |  | Township Establishment | [15 empty] | Blocked |  |  | The informal settlement is located on an environmental sensitive land (stream area) & also encroached on existing cemetery, therefore land availability is the issue. | The informal settlement is located on an environmental sensitive land (stream area) & also encroached on existing cemetery, therefore land availability is the issue. | The project is hindered by environmental & encroachment constraints, therefore it cannot attain any further township establishment milestones.
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Coastal |  |  | East London - Duncan Village New Rest 250 subs (Phase) | C19080108/1 |  | New (2019 - To Date) | Progress Payment Housing Project |  |  | 0 | 0 |  | No | 0 |  | BCMM | 250 | 0 | 0 | 0 |  |  | Township Establishment | [15 empty] | Blocked |  |  | The informal settlement is located on an environmental sensitive land (steep slope; flood area), therefore land availability is the issue. | The informal settlement is located on an environmental sensitive land (steep slope; flood area), therefore land availability is the issue. | The project is hindered by environmental constraints, therefore it cannot attain any further township establishment milestones.
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Midlands |  |  | East London - Eluxolweni 701 subs (Phase) | C19080109/1 |  | New (2019 - To Date) | Progress Payment Housing Project |  |  | 0 | 0 |  | No | 0 |  | BCMM | 701 | 0 | 0 | 0 |  |  | Township Establishment | [20 empty] | Refer project back to BCMM
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Midlands |  |  | East London - Holomisa 120 subs (Phase) | C19080110/1 | Erf 678 Mdantsane unit 4 registered under BCMM | New (2019 - To Date) | Progress Payment Housing Project |  |  | 0 | 0 |  | No | 0 |  | BCMM | 120 | 0 | 0 | 0 |  |  | Township Establishment | [15 empty] | Blocked |  |  | Portion of this project is located on within floodline & accessibility is a challenge. | The project has no GP in place & is located on Erf 678 Mdantsane unit 4 registered under BCMM. | The project is hindered by environmental constraints (floodline), therefore it cannot attain any further township establishment milestones.
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Midlands |  |  | East London - Reeston Jevon 115 subs (Phase) | C19080111/1 | Farm 831/2 is a private land (Farm 831/21) is affected by encroaching informal settlements. | New (2019 - To Date) | Progress Payment Housing Project |  |  | 0 | 0 |  | No | 0 |  | BCMM | 115 | 0 | 0 | 0 |  |  | Township Establishment | [15 empty] | Blocked |  |  | Land owned by BCMM, there are existing informal settlements located on the BCMM land & adjacent to BCMM land (Farm 831/2) is a private land (Farm 831/21) is affected by encroaching informal settlements. | Land owned by BCMM, there are existing informal settlements located on the BCMM land & adjacent to BCMM land (Farm 831/2) is a private land (Farm 831/21) is affected by encroaching informal settlements. | The project is hindered by land constraints, therefore it cannot attain any further township establishment milestones.
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Inland |  |  | Kwt - Zwelitsha Ndlovini / Crossroad 65 subs (Phase) | C19080112/1 |  | New (2019 - To Date) | Progress Payment Housing Project |  |  | 0 | 0 |  | No | 0 |  | BCMM | 65 | 0 | 0 | 0 |  |  | Township Establishment | [18 empty] | ECDHS to provide land description & project status quo. | ECDHS to provide land description & project status quo. | Refer project back to BCMM
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Midlands |  |  | East London - Ladies Park 41 subs (Phase) | C19080118/1 | Farm 1404 ownership still subject to confirmation. | New (2019 - To Date) | Progress Payment Housing Project |  |  | 0 | 0 |  | No | 0 |  | BCMM | 41 | 0 | 0 | 0 |  |  | Township Establishment | [19 empty] | The project has no GP in place & is located on Rem of Farm 1404 ownership still subject to confirmation. | Refer project back to BCMM (New Project).
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Midlands |  |  | East London - Lonwabo 31 subs (Phase) | C19080119/1 | Erf 9696 Mdantsane unit 3 registered under BCMM. | New (2019 - To Date) | Progress Payment Housing Project |  |  | 0 | 0 |  | No | 0 |  | BCMM | 31 | 0 | 0 | 0 |  |  | Township Establishment | [19 empty] | The project has no GP in place & is located on Erf 9696 Mdantsane unit 3 registered under BCMM. | Refer project back to BCMM (New Project).
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Midlands |  |  | East London - Mbekweni 53 subs (Phase) | C19080121/1 | Erf 9695 Mdantsane unit 1 registered under BCMM. | New (2019 - To Date) | Progress Payment Housing Project |  |  | 0 | 0 |  | No | 0 |  | BCMM | 53 | 0 | 0 | 0 |  |  | Township Establishment | [19 empty] | The project has no GP in place & is located on Erf 9695 Mdantsane unit 1 registered under BCMM. | Refer project back to BCMM (New Project).
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Midlands |  |  | East London - Mdantsane Khaylethu 150 subs (Phase) | C19080122/1 | Erf 2021 Mdantsane unit 1 registered under BCMM. | New (2019 - To Date) | Progress Payment Housing Project |  |  | 0 | 0 |  | No | 0 |  | BCMM | 150 | 0 | 0 | 0 |  |  | Township Establishment | [18 empty] | No planning approval yet, currently rezoning for high density development is underway. | The project has no GP in place & is located on Erf 2021 Mdantsane unit 1 registered under BCMM. | Refer project back to BCMM (New Project).
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Midlands |  |  | East London - Mdantsane - Mark Makalima 40 subs (Phase) | C19080123/1 | Erf 476 - 477 Mdantsane unit (Makalima 1); Erven 410-415 & Erven 605;607 (Makalima 2); 608 & 614 Mdantsane unit 1 (Makalima 3) land is owned by BCMM and the land has been invaded. | New (2019 - To Date) | Progress Payment Housing Project |  |  | 0 | 0 |  | No | 0 |  | BCMM | 40 | 0 | 0 | 0 |  |  | Township Establishment | [15 empty] | Blocked |  |  | No planning approval yet, land is too small & cannot accommodate / meet the demand on the ground, therefore alternative land is required. | No GP for this project at this stage & is located on property description Erf 476 - 477 Mdantsane unit (Makalima 1); Erven 410-415 & Erven 605;607 (Makalima 2); 608 & 614 Mdantsane unit 1 (Makalima 3). There are two Makamila informal settlements situated on property decription mentioned above & the land is owned by BCMM and the land has been invaded. | The project is hindered by land constraints, therefore it cannot attain any further township establishment milestones.
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Midlands |  |  | East London - Mdantsane Masibambane 35 subs (Phase) | C19080124/1 | Erf 440 Mdantsane Unit 1 owned by the municipality | New (2019 - To Date) | Progress Payment Housing Project |  |  | 0 | 0 |  | No | 0 |  | BCMM | 35 | 0 | 0 | 0 | 120 | 156 | Township Establishment | [15 empty] | Blocked | There are about only 156 outstanding transfers & 0 constructed houses to date out of none numbered project yield & BCMM has about 0 un issued title deeds that needs to be handed over to the correct beneficiaries. | EC DoHS: To provide progress report on the balance of 156 outstanding transfers; exact no. of approved beneficiaries & total no of constructed houses. | No planning approval yet, land is too small & cannot accommodate / meet the demand on the ground, therefore alternative land is required. | The project has no GP in place & is located on Erf 440 Mdantsane Unit 1 owned by the municipality. The project area has been invaded by informal settlements, therefore the land cannot accomodate the no. of settlements on the ground. Possibly relocations will have to be considered. Contradiction observed regarding status of the GP, therefore ECDHS to confirm. | The project is not known by ECDHS, therefore reffered back to BCMM
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Midlands |  |  | East London - Mdantsane Nkomponi 172 subs (Phase) | C19080125/1 | Erf 2019 Mdantsane Unit 1 owned by the municipality | New (2019 - To Date) | Progress Payment Housing Project |  |  | 0 | 0 |  | No | 0 |  | BCMM | 172 | 0 | 0 | 0 |  |  | Township Establishment | [15 empty] | Blocked |  |  | No planning approval yet, currently rezoning for high density development is underway. | The project has no GP in place & is located on Erf 2019 Mdantsane Unit 1 owned by the municipality. The project area has been invaded by informal settlements further land investigations to determine the capacity of the land is required. | The project is hindered by land invasions, therefore it cannot attain any further township establishment milestones. | This is an informal settlement. The project on procurement of the Professional Team for Design and construction supervision
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Midlands |  |  | East London - Mdantsane Phola Park 150 subs (Phase) | C19080126/1 | Erf 1056 Mdantsane unit 5 owned by the BCMM | New (2019 - To Date) | Progress Payment Housing Project |  |  | 0 | 0 |  | No | 0 |  | BCMM | 150 | 0 | 0 | 0 |  |  | Township Establishment | [15 empty] | Blocked |  |  | No planning approval yet, the site cannot accommodate / meet the demand on the ground. The land belongs to the municipality. | There is a GP no. 1240/2019 in place consisting of 36 erven situated on Erf 1056 Mdantsane unit 5 owned by the BCMM. Possibly relocations may be required in order to align with the layout plan. | The project is hindered by land constraints, therefore it cannot attain any further township establishment milestones.
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Midlands |  |  | East London - Mdantsane Slovo Park 280 subs (Phase) | C19080127/1 | Erven 5130-5141,5144-5162 Mdantsane Unit 5 registered under BCMM | New (2019 - To Date) | Progress Payment Housing Project |  |  | 0 | 0 |  | No | 0 |  | BCMM | 280 | 0 | 0 | 0 |  |  | Township Establishment | [18 empty] | There is a layout & COE's in place approved in terms of Land Use Regulation Act (LURA). Land Survey to confirm the status of GP. | The project area is situated on various properties owned by BCMM i.e. Erven 5130-5141,5144-5162 Mdantsane Unit 5. Currently there is no GP & there are existing structures on the ground (Insitu).Densification is being piloted in one of the erven & GP is targeted for 2024/25 financial year. | Refer project back to BCMM (New Project).
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Midlands |  |  | East London - Mdantsane Stofile Village 75 subs (Phase) | C19080128/1 | Erf 3307 Mdantsane Unit 6 (Open Space) registered under BCMM | New (2019 - To Date) | Progress Payment Housing Project |  |  | 0 | 0 |  | No | 0 |  | BCMM | 75 | 0 | 0 | 0 |  |  | Township Establishment | [15 empty] | Blocked |  |  | No planning approval yet, land is too steep & alternative land is required. The land belongs to BCMM but the other part (piece of land) is a open space, hence alternative land is required. | The project is situated on various properties i.e. Erf 3307 Mdantsane Unit 6 (Open Space) registered under BCMM. Currently there is no GP in place. Informal settlements invaded LM properties on steep land & relocations may be required. | The project is hindered by land constraints, therefore it cannot attain any further township establishment milestones.
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Coastal |  |  | East London - Scenery Park Airport 39 subs (Phase) | C19080129/1 |  | New (2019 - To Date) | Progress Payment Housing Project |  |  | 0 | 0 |  | No | 0 |  | BCMM | 39 | 0 | 0 | 0 |  |  | Township Establishment | [15 empty] | Blocked |  |  | Airport is the informal settlement & hasn’t been planned at al, due to high density of number of households, land is unable to accommodate the number of existing informal settlements (issue land availability). | Airport is the informal settlement & hasn’t been planned at al, due to high density of number of households, land is unable to accommodate the number of existing informal settlements (issue land availability). | The project is hindered by land constraints, therefore it cannot attain any further township establishment milestones.
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Coastal |  |  | East London - Scenery Park Eskom 79 subs (Phase) | C19080130/1 | Erf 33364 registered under Section 21 | New (2019 - To Date) | Progress Payment Housing Project |  |  | 0 | 0 |  | No | 0 |  | BCMM | 79 | 0 | 0 | 0 |  |  | Township Establishment | [15 empty] | Blocked |  |  | Eskom is the informal settlement & hasn’t been planned at al, due to high density of number & land is not available to accommodate the number of existing informal settlements. | The project is located on Erf 33364 registered under Section 21. Eskom is the informal settlement & hasn’t been planned at al, due to high density of number & land is not available to accommodate the number of existing informal settlements. | The project is hindered by land constraints, therefore it cannot attain any further township establishment milestones.
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Coastal |  |  | East London - Scenery Park Ekuphumleni 98 subs (Phase) | C19080131/1 | Erf 43278 East London registered under Section 21 | New (2019 - To Date) | Progress Payment Housing Project |  |  | 0 | 0 |  | No | 0 |  | BCMM | 98 | 0 | 0 | 0 |  |  | Township Establishment | [15 empty] | Blocked |  |  | Ekuphumuleni is the informal settlement & hasn’t been planned at al, due to high density of number & land is not available to accommodate the number of existing informal settlements. | The settlement located on Erf 43278 East London registered under Section 21. There is no GP in place due to no planning; high density of number & land is not available to accommodate the number of existing informal settlements. | The project is hindered by land constraints, therefore it cannot attain any further township establishment milestones.
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Coastal |  |  | East London - Scenery Park Manto 96 subs (Phase) | C19080132/1 | Erf 43278 East London registered under Section 21 | New (2019 - To Date) | Progress Payment Housing Project |  |  | 0 | 0 |  | No | 0 |  | BCMM | 96 | 0 | 0 | 0 |  |  | Township Establishment | [15 empty] | Blocked |  |  | Manto is the informal settlement & hasn’t been planned at al, due to high density of number & land is not available to accommodate the number of existing informal settlements | The project is located on Erf 43278 East London registered under Section 21. Manto is the informal settlement & hasn’t been planned at al, due to high density of number & land is not available to accommodate the number of existing informal settlements | The project is hindered by land constraints, therefore it cannot attain any further township establishment milestones.
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Coastal |  |  | East London - Scenery Park - Phola Park 209 subs (Phase) | C19080133/1 | Erf 40493 East London registered under Section 21 | New (2019 - To Date) | Progress Payment Housing Project |  |  | 0 | 0 |  | No | 0 |  | BCMM | 209 | 0 | 0 | 0 |  |  | Township Establishment | [15 empty] | Blocked |  |  | Phola is the informal settlement & hasn’t been planned at al, due to high density of number & land is not available to accommodate the number of existing informal settlements | The project is located on Erf 40493 East London registered under Section 21. Phola is the informal settlement & hasn’t been planned at al, due to high density of number & land is not available to accommodate the number of existing informal settlements | The project is hindered by land constraints, therefore it cannot attain any further township establishment milestones.
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Midlands |  |  | East London - Zola Park 1, 2 And 3 97 subs (Phase) | C19080134/1 | Erven 9616 (not registered under BCMM); 9617 and 10103 NU3 Zola 1; Erf 9623 NU3 Zola 2 and Erf 9619 NU3 Zola 3 registered under BCMM. | New (2019 - To Date) | Progress Payment Housing Project |  |  | 0 | 0 |  | No | 0 |  | BCMM | 97 | 0 | 0 | 0 |  |  | Township Establishment | [15 empty] | Blocked |  |  |  | The project is situated on Erven 9616 (not registered under BCMM); 9617 and 10103 NU3 Zola 1; Erf 9623 NU3 Zola 2 and Erf 9619 NU3 Zola 3 registered under BCMM. There is no GP for this project. | The project is hindered by land constraints, therefore it cannot attain any further township establishment milestones.
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Coastal |  |  | East London - Duncan Village - Bebelele 1250 subs (Phase) | C19080135/1 |  | New (2019 - To Date) | Progress Payment Housing Project |  |  | 0 | 0 |  | No | 0 |  | BCMM | 1250 | 0 | 0 | 0 |  |  | Township Establishment | [15 empty] | Blocked |  |  | The informal settlement is located on an environmental sensitive land (steep slope; flood area), therefore land availability is the issue. | The informal settlement is located on an environmental sensitive land (steep slope; flood area), therefore land availability is the issue. | The project is hindered by environmental constraints, therefore it cannot attain any further township establishment milestones.
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Midlands |  |  | East London - Mdantsane - Nondula 470 subs (Phase) | C19080136/1 | Erven 11475; 3055 & 3056 Mdantsane Unit 1 (registered under BCMM) | New (2019 - To Date) | Progress Payment Housing Project |  |  | 0 | 0 |  | No | 0 |  | BCMM | 138 | 0 | 0 | 0 |  |  | Township Establishment | [15 empty] | Blocked |  |  | There is a GP 3960/2006 in place with 138 sites / erven, however it be noted that the area is densely populated & there is conformity with the GP. Relocation & alternative land is required. | The GP was surveyed over Erven 11475; 3055 & 3056 Mdantsane Unit 1 (registered under BCMM). There is a GP 3960/2006 in place with 138 sites / erven, however it be noted that the area is densely populated & there is none conformity with the GP. Relocation & alternative land is required. | The project is hindered by non conformity with the GP, therefore it cannot attain any further township establishment milestones. | HDID report indicate that detailed designs were approved & that draft tender documents for sewer & water submitted to BCMM for reviewal.
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Midlands |  |  | East London - Mdantsane - Nazo Park 1 & 2 91 subs (Phase) | C19080137/1 | Both Nazo 1 & 2 are located in Mdantsane Unit 1 under Erf 3046 (Nazo Park 1) and on Erf 3110 (Nazo Park 2) registered under BCMM. | New (2019 - To Date) | Progress Payment Housing Project |  |  | 0 | 0 |  | No | 0 |  | BCMM | 91 | 0 | 0 | 0 |  |  | Township Establishment | [18 empty] | Nazo 1 registered under BCMM, planning studies are required. Nazo 2 land belongs to BCMM planning studies required. | Both Nazo 1 & 2 are located in Mdantsane Unit 1 under Erf 3046 (Nazo Park 1) and on Erf 3110 (Nazo Park 2) registered under BCMM. The project has no GP in place since planning studies are required. | Refer project back to BCMM (New Project).
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Midlands |  |  | East London - Ramaphosa Proper 144 subs (Phase) | C19080138/1 |  | New (2019 - To Date) | Progress Payment Housing Project |  |  | 0 | 0 |  | No | 0 |  | BCMM | 144 | 0 | 0 | 0 |  |  | Township Establishment | [18 empty] | ECDHS to provide property desrcription & status of TE processes | ECDHS to provide property desrcription & status of TE processes | Refer project back to BCMM
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Midlands |  |  | East London - Mdantsane - Ekhupumleni subs (Phase) | C19080139/1 | There are two Ekuphumleni projects that are located on Remainder of Farm 1404 registered under BCMM. The other Ekuphumuleni is in Mdantsane unit 2 & the other Ekuphumeleni is in Mdantsane unit 5. Accordig to the latest land survey report the project is located on Erf 3394 Mdantsane Unit 5 owned by BCMM. | New (2019 - To Date) | Progress Payment Housing Project |  |  | 0 | 0 |  | No | 0 |  | BCMM | 0 | 0 | 0 | 0 |  |  | Township Establishment | [18 empty] | There are two Ekuphumleni projects in the BCMM & both of them were approved in terms of the SPLUMA (Town Planning Approval) & haven't obtained GP approval. | There are two Ekuphumleni projects that are located on Remainder of Farm 1404 registered under BCMM. The other Ekuphumuleni is in Mdantsane unit 2 & the other Ekuphumeleni is in Mdantsane unit 5. The one located in Mdantsnane unit 2 has a yield of 54 residential sites & the other one in Mdantsane unit 5 expected yield is 44 residential sites. Accordig to the latest land survey report the project is located on Erf 3394 Mdantsane Unit 5 owned by BCMM, GP processes underway & is expected to be finalised before the end 2023/24 financial year (Municipal). | Refer project back to BCMM (New Project).
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Midlands |  |  | East London - Mdantsane - Ramaphosa B 144 subs (Phase) | C19080140/1 | In BCMM there are 5 informal settlements named as Ramaphosa. There is Ramaphosa A (two settlements) &B (two settlements) . Ramaphosa A located on Erf 1369 Mdantsane unit 4 registered under BCMM. Ramaphosa B located in Mdantsane unit 4 under Erf 1394 registered under BCMM. The remaining Ramaphosa consisting of 1 settlement & is located on the remainder of farm 1404 registered under BCMM & there is no GP in place for this project. | New (2019 - To Date) | Progress Payment Housing Project |  |  | 0 | 0 |  | No | 0 |  | BCMM | 144 | 0 | 0 | 0 |  |  | Township Establishment | [18 empty] | ECDHS to provide property desrcription & status of TE processes | In BCMM there are 5 informal settlements named as Ramaphosa. There is Ramaphosa A (two settlements) &B (two settlements) . Ramaphosa A located on Erf 1369 Mdantsane unit 4 registered under BCMM. Ramaphosa B located in Mdantsane unit 4 under Erf 1394 registered under BCMM. The remaining Ramaphosa consisting of 1 settlement & is located on the remainder of farm 1404 registered under BCMM & there is no GP in place for this project. | Refer project back to BCMM, not known
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Midlands |  |  | East London Mdantsane - Lilian Ngoyi 61 subs (Phase) | C19080141/1 | Erf 4976 Mdantsane unit 5 registered under BCMM. | New (2019 - To Date) | Progress Payment Housing Project |  |  | 0 | 0 |  | No | 0 |  | BCMM | 61 | 0 | 0 | 0 |  |  | Township Establishment | [15 empty] | Blocked |  |  | No planning approval yet & densely populated, therefore the land cannot accommodate / meet the demand on the ground. | The project is located on Erf 4976 Mdantsane unit 5 registered under BCMM. It is confirmed that there is no GP in place obviously this is due to no planning approval yet & densely populated, therefore the land cannot accommodate / meet the demand on the ground. | The project is hindered by land constraints, therefore it cannot attain any further township establishment milestones.
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Midlands |  |  | East London - Mdantsane - Mlatsheni 67 subs (Phase) | C19080142/1 | The project is located on the Remainder of Farm 1404 East London registered under BCMM. | New (2019 - To Date) | Progress Payment Housing Project |  |  | 0 | 0 |  | No | 0 |  | BCMM | 67 | 0 | 0 | 0 |  |  | Township Establishment | [15 empty] | Blocked |  |  | Land belongs to BCMM & informal settlement located on a steep land / environmental sensitive area therefore alternative land & relocations should be considered. | The project is located on the Remainder of Farm 1404 East London registered under BCMM. The informal settlement located on a steep land / environmental sensitive area & there is no GP to date therefore alternative land & relocations should be considered. | The project is hindered by environmental constraints, therefore it cannot attain any further township establishment milestones.
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Midlands |  |  | East London - Mdantsane - Masizakhe 202 subs (Phase) | C19080143/1 | The project is located on Erven 907 - 911; 9941; 9945; 9946; 921 & 10114 Mdantsane unit 1. The following mentioned Erven are privately registered i.e. 907;909;911&921 with 10114 unregistered (consolidation diagragm. The remaining erven are registered under BCMM i.e. 908; 910; ; 9941;9945 &9946. | New (2019 - To Date) | Progress Payment Housing Project |  |  | 0 | 0 |  | No | 0 |  | BCMM | 202 | 0 | 0 | 0 |  |  | Township Establishment | [15 empty] | Blocked |  |  | No planning approval yet, currently rezoning for high density development is underway. | The project is located on Erven 907 - 911; 9941; 9945; 9946; 921 & 10114 Mdantsane unit 1. The following mentioned Erven are privately registered i.e. 907;909;911&921 with 10114 unregistered (consolidation diagragm. The remaining erven are registered under BCMM i.e. 908; 910; ; 9941;9945 &9946. No planning approval yet, currently rezoning for high density development is underway & there is no GP in place. | The project is hindered by land constraints, therefore it cannot attain any further township establishment milestones.
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Midlands |  |  | East London - Mdantsane - Elukhanyisweni 24 subs (Phase) | C19080144/1 | The project is located on Erf 5102 Mdantsane Unit 2 registered under BCMM. | New (2019 - To Date) | Progress Payment Housing Project |  |  | 0 | 0 |  | No | 0 |  | BCMM | 24 | 0 | 0 | 0 |  |  | Township Establishment | [15 empty] | Blocked |  |  | No planning approval yet, the area is steep & alternative land may be required and is subject to TRA. | The project is located on Erf 5102 Mdantsane Unit 2 registered under BCMM. To date there is no GP in place since there is even no planning approval yet, the area is steep & alternative land may be required and is subject to TRA. | The project is hindered by land constraints, therefore it cannot attain any further township establishment milestones.
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Midlands |  |  | East London - Mdantsane - Zimele 52 subs (Phase) | C19080145/1 | The property descriptions are Erven 10441; 10442; 10446 - 10448 Mdantsane unit 3 registered under BCMM. There is also another piece of land named as Erf 9615 Mdantsane unit 3 registered under BCMM. | New (2019 - To Date) | Progress Payment Housing Project |  |  | 0 | 0 |  | No | 0 |  | BCMM | 52 | 0 | 0 | 0 |  |  | Township Establishment | [15 empty] | Blocked |  |  | Zimele is situated on a private land under a institutional zoned area. The site has been invaded (School site). Alternative land & relocations is required. | The property descriptions are Erven 10441; 10442; 10446 - 10448 Mdantsane unit 3 registered under BCMM. There is also another piece of land named as Erf 9615 Mdantsane unit 3 registered under BCMM & there is Masixole High School that has been invaded. Alternative land & relocations is required. There is no GP for this project. | The project is hindered by land constraints, & invasion to the school site therefore it cannot attain any further township establishment milestones.
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Midlands |  |  | East London - Mdantsane - Winnie 99 subs (Phase) | C19080146/1 |  | New (2019 - To Date) | Progress Payment Housing Project |  |  | 0 | 0 |  | No | 0 |  | BCMM | 99 | 0 | 0 | 0 |  |  | Township Establishment | [18 empty] | ECDHS to provide property description and status report on TE processes. | ECDHS to provide property description and status report on TE processes. | Refer project back to BCMM
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Midlands |  |  | East London - Mdantsane - Ekuphumleni 72 subs (Phase) | C19080147/1 | There are two Ekuphumleni projects located on Remainder of Farm 1404 registered under BCMM. The other Ekuphumuleni is in Mdantsane unit 2 & the other Ekuphumeleni in Mdantsane unit 5. | New (2019 - To Date) | Progress Payment Housing Project |  |  | 0 | 0 |  | No | 0 |  | BCMM | 72 | 0 | 0 | 0 |  |  | Township Establishment | [18 empty] | There are two Ekuphumleni projects in the BCMM & both of them were approved in terms of the SPLUMA (Town Planning Approval) & haven't obtained GP approval. | There are two Ekuphumleni projects located on Remainder of Farm 1404 registered under BCMM. The other Ekuphumuleni is in Mdantsane unit 2 & the other Ekuphumeleni in Mdantsane unit 5. The one located in Mdantsane unit 2 has a yield of 54 residential sites & the other one in Mdantsane unit 5 expected yield is 44 residential sites. GP processes underway & is expected to be finalised before the end 2023/24 financial year (Municipal). | Refer project back to BCMM (New Project).
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Midlands |  |  | East London - Jf Mati 89 subs (Phase) | C19080148/1 | The project is located on Erf 91,92,93, 58 AND 79 Mdantsane Unit 4 registered under BCMM & there is no GP in place. | New (2019 - To Date) | Progress Payment Housing Project |  |  | 0 | 0 |  | No | 0 |  | BCMM | 89 | 0 | 0 | 0 |  |  | Township Establishment | [19 empty] | The project is located on Erf 91,92,93, 58 AND 79 Mdantsane Unit 4 registered under BCMM & there is no GP in place. | Refer project back to BCMM (New Project).
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Midlands |  |  | East London - Mdantsane - Duma Nokhwe A 29 subs (Phase) | C19080149/1 | Duma Nokhwe A located on Erf 6169 Mdantsane unit 2 (Ownership still to be confimed/required). | New (2019 - To Date) | Progress Payment Housing Project |  |  | 0 | 0 |  | No | 0 |  | BCMM | 29 | 0 | 0 | 0 |  |  | Township Establishment | [18 empty] | Land belongs to BCMM, however the area is densely populated thereofre alternative land & relocations is required. | There are four settlememts named as Duma Nokhwe i.e. Duma Nokhwe A located on Erf 6169 Mdantsane unit 2 (Ownership still to be confimed/required); Duma Nokhwe B which has two regions (B1&B2) & Duma Nokhwe C are located on the Remainder of Farm 1404 East London registered under BCMM. There is no GP in place. | Refer project back to BCMM (New Project).
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Midlands |  |  | East London - Mdantsane - Duma Nokhwe B 62 subs (Phase) | C19080150/1 | Duma Nokhwe B which has two regions (B1&B2) & Duma Nokhwe C are located on the Remainder of Farm 1404 East London registered under BCMM. | New (2019 - To Date) | Progress Payment Housing Project |  |  | 0 | 0 |  | No | 0 |  | BCMM | 62 | 0 | 0 | 0 |  |  | Township Establishment | [18 empty] | Land belongs to BCMM & planning hasn’t yet been undertaken. Planning studies / investigations are required. | There are four settlememts named as Duma Nokhwe i.e. Duma Nokhwe A located on Erf 6169 Mdantsane unit 2 (Ownership still to be confimed/required); Duma Nokhwe B which has two regions (B1&B2) & Duma Nokhwe C are located on the Remainder of Farm 1404 East London registered under BCMM. There is no GP in place. | Refer project back to BCMM (New Project).
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Midlands |  |  | East London - Mdantsane Duma Nokhwe C 84 subs (Phase) | C19080151/1 | Duma Nokhwe B which has two regions (B1&B2) & Duma Nokhwe C are located on the Remainder of Farm 1404 East London registered under BCMM. | New (2019 - To Date) | Progress Payment Housing Project |  |  | 0 | 0 |  | No | 0 |  | BCMM | 84 | 0 | 0 | 0 |  |  | Township Establishment | [18 empty] | Land belongs to BCMM, the informal settlement is located in an environmental sensitive area. Alternative land & relocations should be considered. | There are four settlememts named as Duma Nokhwe i.e. Duma Nokhwe A located on Erf 6169 Mdantsane unit 2 (Ownership still to be confimed/required); Duma Nokhwe B which has two regions (B1&B2) & Duma Nokhwe C are located on the Remainder of Farm 1404 East London registered under BCMM. There is no GP in place. | The project is hindered by land constraints, therefore it cannot attain any further township establishment milestones.
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Midlands |  |  | East London - Mdantsane - Vukani Park 125 subs (Phase) | C19080152/1 | The project is located on the Remainder of Farm 1404 East London registered under BCMM. There is no GP in place. | New (2019 - To Date) | Progress Payment Housing Project |  |  | 0 | 0 |  | No | 0 |  | BCMM | 125 | 0 | 0 | 0 |  |  | Township Establishment | [18 empty] | ECDHS to provide property description and status report on TE processes. | The project is located on the Remainder of Farm 1404 East London registered under BCMM. There is no GP in place. | Refer project back to BCMM
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Inland |  |  | KWT - Dimbaza South Ext 3-phola Park 35 subs (Phase) | C19080153/1 |  | New (2019 - To Date) | Progress Payment Housing Project |  |  | 0 | 0 |  | No | 0 |  | BCMM | 35 | 0 | 0 | 0 | 185 |  | Township Establishment | [18 empty] | Township has been upgraded in terms of the land tenure (SPLUMA) for the whole Dimbaza township including pre 94 housing. | TBC | Refer project back to BCMM (New Project).
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Coastal |  |  | East London - Duncan Village - Diphini 590 subs (Phase) | C19090002/1 |  | New (2019 - To Date) | Progress Payment Housing Project |  |  | 0 | 0 |  | No | 0 |  | BCMM | 590 | 0 | 0 | 0 |  |  | Township Establishment | [15 empty] | Blocked |  |  | The informal settlement is located on an environmental sensitive land (steep slope; flood area), therefore land availability is the issue. | The informal settlement is located on an environmental sensitive land (steep slope; flood area), therefore land availability is the issue. | The project is hindered by land & environmental constraints, therefore it cannot attain any further township establishment milestones.
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Inland |  |  | KWT - Ginsberg 50 subs (Phase) | C20110009/1 |  | New (2019 - To Date) | Progress Payment Housing Project |  |  | 0 | 0 |  | No | 0 |  | BCMM | 50 | 0 | 0 | 0 |  |  | Township Establishment | [18 empty] | ECDHS to provide property description & project status quo. | ECDHS to provide property description and status report on TE processes. GP is subject to confirmation. | Refer project back to BCMM
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Inland |  |  | KWT - Dimbaza Phola Park 570 subs (Phase) | C21020001/1 |  | New (2019 - To Date) | Progress Payment Housing Project |  |  | 0 | 0 |  | No | 0 |  | BCMM | 570 | 0 | 0 | 0 |  |  | Township Establishment | [18 empty] | Township has been upgraded in terms of the land tenure (SPLUMA) for the whole Dimbaza township including pre 94 housing. | TBC | Refer project back to BCMM (New Project).
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Inland |  |  | KWT - Dimbaza Shutter Proof 739 Subs (Phase) | C21090002/1 |  | New (2019 - To Date) | Progress Payment Housing Project |  |  | 0 | 0 |  | No | 0 |  | BCMM | 739 | 0 | 0 | 0 |  |  | Township Establishment | [18 empty] | Township has been upgraded in terms of the land tenure (SPLUMA) for the whole Dimbaza township including pre 94 housing. | TBC | Refer project back to BCMM (New Project).
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Inland |  |  | KWT - Litha North 160 Subs (Phase) | C21090003/1 |  | New (2019 - To Date) | Progress Payment Housing Project |  |  | 0 | 0 |  | No | 0 |  | BCMM | 160 | 0 | 0 | 0 |  |  | Township Establishment | [18 empty] | ECDHS to provide property description, however according to planning the GP are in place for the whole project area. Planning approval obtained around 2005/6 fy. | GP no.993/2007 is in place & is confirmed for this project area. | Updates on bulk & internal services confirmed
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Inland |  |  | KWT - Berlin Majarinteyeni 150 Subsidies (Phase) | C21120002/1 |  | New (2019 - To Date) | IRDP - Housing Construction Project Linked |  |  | 0 | 0 |  | No | 0 |  | BCMM | 150 | 0 | 0 | 0 |  |  | Township Establishment | [15 empty] | Blocked |  |  | The project requires installation of internal services. | Confirmed that GP is in place for this project (2018). | No HSS number on the PRM & the project is not not known by ECDHS.
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Inland |  |  | KWT - Golf Course (Phase) | C21120003/1 |  | New (2019 - To Date) | IRDP - Housing Construction Project Linked |  |  | 0 | 0 |  | No | 0 |  | BCMM | 0 | 0 | 0 | 0 |  |  | Township Establishment | [18 empty] | TR is in place & it looks like some transfers have been undertaken. ECDHS to report progress regarding construction activities etc. | ECDHS to confirm property description & project status quo. | Refer project back to BCMM
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Coastal | 32.8795S | 27.3898 | East London - Parkridge - 78 subs (Phase 1) | C95090002/1 -2 |  | Post 94 (1994 - 2014) | Progress Payment Housing Project | 1995-10-01 | 28/02/2023 | 13894695.12 | 10082377.67 | Yes | Yes | 3520000 |  | ECDHS | 78 | 78 | 78 | 78 |  |  | Township Establishment | [15 empty] | Active |  |  | ECDHS to provide property description ( project location) & status report. | ECDHS to provide property description ( project location) & status report. | Updates on bulk & internal services confirmed. Rectification 78
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Inland | -32.8912 | 27.3763 | KWT - Sweetwaters Ph 1 - 800 subs (Phase 1) | C95100005/1 - 2 |  | Post 94 (1994 - 2014) | Progress Payment Housing Project | 1996-04-01 | 28/02/2023 | 16929795.79 | 16871286.89 | Yes | Yes | 2680359.2 |  | ECDHS | 800 | 801 | 800 | 800 |  |  | Township Establishment | [15 empty] | Active |  |  | GP is in place & land use management to confirm the status of compliance certificate. | GP is in place & Infrastructure to confirm the status of availability of services. | Updates on bulk & internal services confirmed. Rectification 20
Eastern Cape | Buffalo City Metro | Buffalo City Metro |  |  |  | East London - Erf 945 - 242 subs (Phase 1) | C96030001/1 |  | Post 94 (1994 - 2014) | Progress Payment Housing Project | 1996-01-01 | 1998-09-30 | 1100000 | 1100000 |  | No | 0 |  | ECDHS | 242 | 223 | 242 | 242 |  |  | Township Establishment | [20 empty] | Project is not known ECDHS officials, guidance is required from National Dept
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Coastal |  |  | East London - Braelynn Ext 8 - 69 subs (Phase 1) | C96060003/1 |  | Post 94 (1994 - 2014) | Progress Payment Housing Project |  |  | 345000 | 345000 |  | No | 0 |  | ECDHS | 69 | 91 | 69 | 69 |  |  | Township Establishment | [18 empty] | ECDHS to provide property description & status quo for the project. | ECDHS to provide property description & status quo for the project. | Updates on bulk & internal services confirmed
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Coastal |  |  | East London - Braelynn Ext 10 - 649 subs (Phase 1) | C96080006/1 | The project is located on Erven 2376;2377; 1844; 4585 & 68406 East London registered under BCMM. ECDHS to provide project status quo for the project. | Post 94 (1994 - 2014) | Progress Payment Housing Project |  |  | 9542220 | 9542220 |  | No | 0 |  | ECDHS | 648 | 646 | 649 | 648 | 1 |  | Transfer Stage | [15 empty] | Blocked |  |  | ECDHS to provide property description & status quo for the project. | The project is located on Erven 2376;2377; 1844; 4585 & 68406 East London registered under BCMM. ECDHS to provide project status quo for the project. | Progress regarding transfers to be obtianed from Mr Fihla & should populate columns W&X. | HDID report indicate that invasions affected this project hence blocked. Internal services designs were approved.
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Midlands |  |  | East London - Potsdam South - 531 subs (Phase 1) | C96090006/1 |  | Post 94 (1994 - 2014) | Progress Payment Housing Project | 1996-09-08 | 1998-08-31 | 7304492.5 | 7304492.5 |  | No | 0 |  | ECDHS | 531 | 530 | 531 | 524 |  |  | Township Establishment | [18 empty] | ECDHS to provide property description & status quo for the project. Land is issue since it very densely populated. | ECDHS to provide property description & status quo for the project. Land is issue since it very densely populated. | Historic project & is not known by ECDHS.
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Inland |  |  | KWT - Dimbaza Ph 1 - 776 subs (Phase 1) | C97030003/1 | GP is confirmed & in place for Dimbaza area | Post 94 (1994 - 2014) | Progress Payment Housing Project | 1996-01-01 | 2023-02-28 | 26867699.74 | 16862226.5 |  | No | 0 |  | ECDHS | 776 | 776 | 776 | 776 |  |  | Township Establishment | [18 empty] | Township has been upgraded in terms of the land tenure (SPLUMA) for the whole Dimbaza township including pre 94 housing. | GP is confirmed & in place for Dimbaza area | Updates on bulk & internal services confirmed
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Coastal |  |  | East London - Area P (Egoli) - 382 subs (Phase 1) | C97090005/1; C09110005/1 | The project is located on Erven 1127;1128 & 1826 East London registered under BCMM & there is no GP in place. Area P Egoli is to be reported by the ECDHS regarding status quo. | Post 94 (1994 - 2014) | Progress Payment Housing Project | 2015-11-02 | 2019-04-30 | 56086705.77 | 54988196.46 |  | No | 0 |  | ECDHS | 382 | 382 | 382 | 382 |  |  | Township Establishment | [18 empty] | Area P Egoli is to be reported by the ECDHS regarding status quo | The project is located on Erven 1127;1128 & 1826 East London registered under BCMM & there is no GP in place. Area P Egoli is to be reported by the ECDHS regarding status quo. | Updates on bulk & internal services confirmed. Rectification
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Inland |  |  | KWT - Sweetwaters Ph 2 - 800 subs (Phase 1) | C97090007/1 |  | Post 94 (1994 - 2014) | Progress Payment Housing Project | 1997-09-01 | 1999-06-30 | 13800000 | 13800000 |  | No | 0 |  | ECDHS | 800 | 800 | 800 | 800 |  |  | Township Establishment | [18 empty] | GP is in place & land use management to confirm the status of compliance certificate. | GP is in place & Infrastructure to confirm the status of availability of services. | Updates on bulk & internal services confirmed
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Coastal |  |  | East London - Windyridge Flats - 95 subs (Phase 1) | C97090010/1 |  | Post 94 (1994 - 2014) | Progress Payment Housing Project | 1997-06-01 | 1998-12-31 | 1342325 | 1342325 |  | No | 0 |  | ECDHS | 95 | 94 | 93 | 95 |  |  | Township Establishment | [18 empty] | The project is not known by BCMM planning unit, so ECDHS to provide information & property descriptions. | The project is not known by BCMM planning unit, so ECDHS to provide information & property descriptions. | Project is not known ECDHS officials, guidance is required from National Dept
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Coastal |  |  | East London - Haven Hills Ext 10 - 113 subs (Phase 1) | C97120002/1 |  | Post 94 (1994 - 2014) | Progress Payment Housing Project | 1997-08-01 | 1998-07-31 | 587500 | 587500 |  | No | 0 |  | ECDHS | 113 | 122 | 113 | 113 |  |  | Township Establishment | [18 empty] | All Haven Hills are to be reported by the ECDHS regarding status quo | All Haven Hills are to be reported by the ECDHS regarding status quo | Urban project should be reffered back to BCMM
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Inland | -32.928 | 27.9029 | KWT - Phakamisa South - 950 subs ( - Top structure) | C97120012/1 - 5 |  | Post 94 (1994 - 2014) | Progress Payment Housing Project | 1997-06-01 | 2023-09-15 | 150612113.76 | 143783276.43 | Yes | Yes | 3781830 |  | ECDHS | 950 | 951 | 520 | 857 |  |  | Township Establishment | [15 empty] | Active |  |  | Land assembly hasn’t been concluded, because the existing houses are registered under provincial dept. | There seems to be two GP's for Phakamisa project, first one being GP 3797/1999 where transfers have been undertaken & GP 2516/2009 no transfers have been undertaken, therefore ECDHS to confirm the status of the TR / project as a whole. | Updates on bulk & internal services confirmed, this project appears as rural / urban??? | HDID report indicate an 8.4 km of road project for Phakamisa South that is being implemented in phases dueto financial constraint.
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Coastal | -32.935 | 27.4615 | East London - Airport phase 2:195subs (Phase 1) | C98040004/1 |  | Post 94 (1994 - 2014) | Peoples Housing Process (IRDP) | 1998-05-01 | 1999-02-28 | 5559573 | 5559573 | Yes | Yes | 2508748.22 |  | ECDHS | 195 | 195 | 195 | 189 | 195 | 0 | Transfer Stage | [16 empty] | All township establishment milestones have been achieved & to date only 189 houses constructed out of 195 houses, so update is required on contruction activities & handing out of title to the beneficiaries. | EC DHS: To confirm the no. of houses constructed to date, since at the moment only there are 189 houses out of 195 houses (Progress Report). BCMM: To report progress on the 88 title deeds that are in the possession of the LM that are to be issued to the rightful beneficiaries. | ECDHS to confirm the exact number of constructed units & thereafter where applicable prepare a close out report in respect to this project. Suspected GP 645/2003. | ECDHS to confirm the exact number of constructed units & thereafter where applicable prepare a close out report in respect to this project. Suspected GP 645/2003. | Both EDHS & BCMM to update information relating to column X; Y & Z. According to the 24/25 BP R24 915 is budgeted for transfers of 15 properties (target).
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Coastal |  |  | East London - Cambridge - 222 subs (Phase 1) | C98040010/1 - 2 | Erf 54163 East London registered under BCMM | Post 94 (1994 - 2014) | Progress Payment Housing Project | 2000-06-08 | 28/02/2023 | 12099396.54 | 11975948.73 |  | No | 0 |  | ECDHS | 222 | 227 | 222 | 222 |  |  | Township Establishment | [16 empty] | It is not clear out of the 4 HSS project (Cambridge) which one should be the correct project name to use going forward | ECDoHS to confirm the correct HSS project name & also should provide the status quo report for further scrutiny. | GP is place GP6598/2001, Land use to give update on compliance certiticate | The project is located on Erf 54163 East London registered under BCMM & there is a GP6598/2001 in place. Engineering & Land use to give update on compliance certiticate. | Updates on bulk & internal services confirmed. Rectification 51
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Coastal |  |  | East London - Airport phase 1 - 838 subs (Phase 1) | C98060001/1 |  | Post 94 (1994 - 2014) | Progress Payment Housing Project | 1995-01-01 | 1999-03-31 | 10717160 | 10717160 |  | No | 0 |  | ECDHS | 838 | 838 | 840 | 821 | 835 | 3 | Beneficiary Management | [16 empty] | There are affected title deeds whereby the Province needs to appoint conveyancers for rectification of titles. To date there are 43 titles deeds that havent been taken by the beneficiries. | EC DHS: To prepare & regularly update the SCM report regarding the appointment of conveyencers for this project. BCMM: To undertake beneficiary verification exercise and also familiarise themselves with the contetnt of the following policies i.e. Missing Beneficiary Policy; Dispute & Regularisation Policy and therafter start implementation and report regularly in this regards. | ECDHS to confirm project location & property description. Rectification of title deeds is required. Provincial Dept to advise on SCM processes whether it on bid spec; bid evaluation or adjudication. | ECDHS to confirm project location & property description. Rectification of title deeds is required. Provincial Dept to advise on SCM processes whether it on bid spec; bid evaluation or adjudication. | ECDHS to report on status of SCM processes & it be noted that the recommendation suggest that the scope of work should include beneficiary verification & rectification of title deeds for this project to enable for project close out.
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Coastal |  |  | East London - Amalinda Forest - 431 sites (Phase 1) | C98070004/1 |  | Post 94 (1994 - 2014) | Progress Payment Housing Project | 2000-11-01 | 2001-02-28 | 6465000 | 6465000 |  | No | 0 |  | ECDHS | 431 | 431 | 431 | 431 | 408 | 23 | Transfer Stage | [16 empty] | To date only 23 is reported as the balance to transfer (Backlog), EC DoHS to confirm whether conveyancer has been assigned to finish the balance of 23 transfers & BCMM to report on the status of issuing the 172 title deeds to the rightful beneficiaries. | EC DoHS: To provide the status quo / progress report on conveyancing activities since at this stage the backlog is recorded to 23 outstanding transfers. BCMM: To report regularly the number of issued title deeds to the rightful bebeficiaries, since to date there are about 172 un issued title deeds. | ECDHS to report the status quo of this project & should provide us with the land / property description. | ECDHS to report the status quo of this project & should provide us with the land / property description. | Progress regarding transfers to be obtianed from Mr Fihla (ECDHS) & should populate columns W&X.
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Coastal |  |  | East London - Braelynn 2419 - 30 subs (Phase 1) | C98080029/1 |  | Post 94 (1994 - 2014) | Progress Payment Housing Project |  |  | 190500 | 190500 |  | No | 0 |  | ECDHS | 30 | 31 | 30 | 30 |  |  | Township Establishment | [18 empty] | ECDHS to provide property description & status quo for the project. | ECDHS to provide property description & status quo for the project. | Updates on bulk & internal services confirmed
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Inland |  |  | KWT - Ginsberg - 809 subs (Phase 1) | C98100005/1 |  | Post 94 (1994 - 2014) | Progress Payment Housing Project | 1998-10-01 | 2000-02-29 | 11948179.13 | 11948179.17 |  | No | 0 |  | ECDHS | 809 | 816 | 809 | 809 |  |  | Beneficiary Management | [16 empty] | Contradictions between HSS & municipal report have been observed i.e. project yield (809) versus municipal report on properties to be transferred (988). Two number of approved beneficiaries exceeds the project yield hence updates are required. | EC DoHS: To address contradictions & provide correct figures i.e. project yield; no. of approved beneficiaries & etc. | All township establishment stages have been accomplished, beneficiary management including status on transfers & handing over is required from either the Province / BCMM. | All township establishment stages have been accomplished, beneficiary management including status on transfers & handing over is required from either the Province / BCMM. | Both ECDHS & BCMM to update progress relating to transfers in column W & X
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Inland |  |  | KWT - Brickview - 43 subs (Phase 1) | C99030011/1 |  | Post 94 (1994 - 2014) | Progress Payment Housing Project | 1999-10-01 | 1999-12-14 | 610040 | 610040 |  | No | 0 |  | ECDHS | 43 | 40 | 43 | 43 |  |  | Township Establishment | [18 empty] | ECDHS to provide property description & status quo for the project. | ECDHS to provide property description & status quo for the project. | Refer it back to BCMM, project is not known
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Inland |  |  | KWT - Dimbaza Ph 2 - 1720 subs (Phase 1) | C99030015/1 - 2; C09090003/1 |  | Post 94 (1994 - 2014) | Progress Payment Housing Project | 1999-02-01 | 28/02/2023 | 96902291.73 | 68489228.25 |  | No | 0 |  | ECDHS | 1720 | 1718 | 1720 | 1719 |  |  | Township Establishment | [18 empty] | Township has been upgraded in terms of the land tenure (SPLUMA) for the whole Dimbaza township including pre 94 housing. | GP is confirmed & in place for Dimbaza area | Updates on bulk & internal services confirmed. Rectification 291
Eastern Cape | Buffalo City Metro | Buffalo City Metro |  |  |  | East London - Sinebhonge Village - 100 subs (Phase 1) | C99050002/1 |  | Post 94 (1994 - 2014) | Progress Payment Housing Project | 1999-05-17 | 2000-03-24 | 1840000 | 1840000 |  | No | 0 |  | ECDHS | 100 | 100 | 100 | 100 |  |  | Township Establishment | [20 empty] | Refer it back to BCMM, project is not known
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Coastal |  |  | East London - Haven Hills Ext 9 - 6 subs (Phase 1) | C99060001/1 |  | Post 94 (1994 - 2014) | Progress Payment Housing Project | 1998-03-02 | 1998-12-31 | 43500 | 43500 |  | No | 0 |  | ECDHS | 6 | 7 | 6 | 6 |  |  | Township Establishment | [18 empty] | All Haven Hills are to be reported by the ECDHS regarding status quo | All Haven Hills are to be reported by the ECDHS regarding status quo | Urban project should be reffered back to BCMM
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Coastal |  |  | East London - Duncan Village DVRI 323 ( - 30 subs Military Veterans) | C10110025/2 |  | Post 94 (1994 - 2014) | Progress Payment Housing Project | 2021-04-14 | 2023-03-31 | 12970814.63 | 5364771.16 | Yes | Yes | 10000000 |  | BCMM | 30 | 23 | 0 | 0 |  |  | Township Establishment | [14 empty] | Yes | Active | [5 empty] | The HDID report indicate that the project is affected by DV Forum hence contract will be reneweed for the contractor.
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Midlands |  |  | East London - Potsdam Unit P - 900 subs (Phase 1) | C04040021/1 | Erf 5295 Potsdam registered under BCMM | Post 94 (1994 - 2014) | Peoples Housing Process (IRDP) | 2011-11-14 | 2013-11-14 | 71000000 | 0 | No | No | 0 |  | BCMM | 2003 | 500 | 2003 | 900 |  |  | Transfer Stage | [7 empty] | GP 343/2004 | [8 empty] | It is not clear out of the 2 HSS project (Potsdam Unit P) which one should be the correct project name to use going forward | ECDoHS to confirm the correct HSS project name & also should provide the status quo report for further scrutiny. | Planning approval obtained in terms of LEFTEA between 2004 & 2006 on Erf 5295 Potsdam covering all Potsdam Unit P projects | There is a GP no. 343/2004 in place situated on Erf 5295 Potsdam registered under BCMM & consists of 2 528 erven covering all Potsdam Unit P projects. There are transfers that have taken place. | Both ECDHS & BCMM to update progress relating to transfers in column W & X | This project was constructed, completed and handed over to righful beneficiaries by BCMM for 2003 internal services & 900 top structure houses. the balance of 1103 top structure houses was constructed by PHoHS.
Eastern Cape | Buffalo City Metro | Buffalo City Metro | Coastal |  |  | East London - Second Creek 265 subs (Phase 1) | C09060001/1 - 2 |  | Post 94 (1994 - 2014) | Progress Payment Housing Project | 2013-11-01 | 2022-03-31 | 24589646.7 | 24372491.2 |  | No | 0 |  | BCMMDHS | 265 | 265 | 265 | 265 |  |  | Township Establishment |  |  | Yes | Yes |  |  |  | Yes GP NO:146/2011 | Yes | Yes |  |  |  |  | Yes | Completed | This project was implented, completed and houses were handed over to righful beneficiaries | None | ECDHS to provide property description & project status quo report. | ECDHS to provide property description & project status quo report. | Bulk & internal services available | Project complete, there are 11 erves with constructed houses that need to be changed to new erves as they were relocated from old erves due to undevelopable sites.
Key / Legend
|  | Colour | Activitity
Achieved Milestones
Point of Focus
No Progress
Confirmation Required
Generic Milestones (Column Y)
Township Establishment:
Beneficiary Management:
Transfer:
Construction of Houses:
Completed / Close Out:
Note on AB3: Ayanda Zulu: Is the service provider appointed to undertake activities between columns Y to AG. If there are multiple service providers, please provide details in the comment column AN.